## Summary
The Council — AIMS Objectives, Risk Treatment and Improvement Plan
AIG-AIMS-03 · v1.2 draft · Draft for Council review · OFFICIAL · ISO/IEC 42001:2023
Purpose: translate the proposed AIMS scope and control design into measurable objectives, treated risks, opportunities and controlled implementation actions.
Status statement: all objectives, risk scores, treatments, opportunities and improvement actions are proposed starting positions. The Council must validate and approve owners, resources, baselines, targets, dates and risk decisions before use.
Document control | Controlled value |  | Objective readiness |  | Risk and improvement readiness
Document ID | AIG-AIMS-03 |  | Measure | Result | Measure | Result
Version | 1.2 draft |  | Proposed objectives |  | AIMS-level risks
Status | Draft for Council review |  | Approved / active |  | Critical / high inherent
Document owner | AI Governance Lead |  | At risk |  | Residual ratings complete
Approving authority | To be confirmed under Council delegations |  | Average progress |  | Risk QA complete
Effective date | Pending formal approval |  | Objectives with target dates |  | Opportunities
Review frequency | Monthly during implementation; at least quarterly thereafter |  | Last reviews recorded |  | Improvement actions
Source position | AIG-AIMS-01, AIG-AIMS-02 and AI Governance Playbook (AIG-GOV-02, current controlled version per AIG-GOV-03) |  | Objective QA complete |  | Actions complete
Classification | OFFICIAL |  |  |  | Action QA complete
Inherent risk profile |  |  | Objective status |  | Improvement status
Critical |  |  | Draft |  | Not started
High |  |  | Approved |  | Planned
Medium |  |  | Active |  | In progress
Low |  |  | At risk |  | Blocked
|  |  | Achieved |  | Complete
|  |  | Paused |  | Cancelled
Closed
Recommended adoption sequence
1. Confirm accountable ownership, approval authority and the proposed AIMS scope (AIG-AIMS-01).
2. Validate the 38 Annex A decisions against the Council’s licensed standard and approve AIG-AIMS-02.
3. Approve policy, objectives, risk criteria, risk acceptance and the implementation programme.
4. Establish roles, competence, applicable requirements, inventory completeness and controlled evidence arrangements.
5. Pilot the full lifecycle, supplier controls and monitoring on representative real AI systems.
6. Exercise incident and corrective-action processes, then conduct the first internal audit.
7. Complete management review; update objectives, risks, SoA and improvement priorities from evidence.
Version | Date | Change |  |  | Author / owner
1.0 draft | 2026-08-07 | Initial AIMS objectives, risk treatment, opportunities and improvement plan mapped to the AI Governance Playbook (AIG-GOV-02), AIG-AIMS-01 and AIG-AIMS-02. |  |  | AI Governance Lead
1.1 draft | 28 September 2026 | Correct risk-tier boundaries, residual-rating thresholds and objective QA colours.
1.2 draft | 29 September 2026 | QA remediation — applied findings QA-074, QA-214, QA-218, QA-220, QA-238, QA-240, QA-241, QA-243, QA-251, QA-254, QA-281, QA-284, QA-291 (see QA change log). Residual scoring now uses the Playbook §4.4.3 control-effectiveness factor. |  |  | AI Governance Lead

## AIMS Objectives
The Council — AIMS Objectives Register
AIG-AIMS-03 · v1.2 draft · Draft for Council review · OFFICIAL
Purpose: define proposed measurable AIMS objectives, owners, evidence, review arrangements and progress.
Current position: the eight entries are draft management-system objectives. Baselines, targets, dates, resources and approval must be validated before they become Council commitments.
Objective ID | Objective statement | Intended outcome | ISO / SoA links | Related AIMS risks | Measure | Baseline | Proposed target | Target date | Proposed owner | Supporting roles | Review cadence | Evidence source | Status | Current performance | Progress % | Last reviewed | Decision / next action | Record QA
OBJ-01 | Maintain a complete and current inventory of in-scope AI activity. | Leadership has reliable visibility of every Council AI use, its owner, lifecycle status and governance tier. | ISO 6.2; A.4.2; A.8.5; A.9.2 | R-02, R-03 | Percentage of known in-scope AI systems with a valid AI Register ID, accountable owner, AGPI tier, lifecycle status and review date. | Not established — inventory completeness review required. | Proposed: 100% of known in-scope systems complete; quarterly completeness checks and documented shadow-AI follow-up. |  | AI Governance Lead | Service Owners; Digital; Data; Procurement; Security; Internal Audit | Monthly during implementation; quarterly when established | AIG-INV-04 AI Register; AIG-OPS-06 Dashboard; completeness-review records | Draft | Not measured | 0% |  | Approve the metric definition, data owner, completeness-testing method and target date.
OBJ-02 | Apply proportionate governance and approval before AI deployment or material change. | AI systems progress through traceable, risk-tiered decisions with conditions closed before operational use. | ISO 6.2, 8.1; A.5.2-A.5.5; A.6.2.2-A.6.2.6; A.9.2 | R-01, R-03, R-04 | Percentage of high/critical cases with complete required assessments, authorised decision record and no open critical go-live condition. | Not established — live case baseline required. | Proposed: 100% before go-live or material change; zero operational systems with an unresolved critical approval condition. |  | AI Governance Lead / Service Owner | Governance bodies; Legal; DPO; Equality; Security; Procurement | At every decision gate; monthly portfolio review | AIG-INV-03, AIG-INV-04, AIG-ASS-01, AIG-ASS-02, AIG-ASS-03, AIG-ASS-04, AIG-ASS-05, AIG-ASS-06, AIG-ASS-07, AIG-ASS-08, AIG-ASS-09, AIG-ASS-10 and AIG-DEC-03; AIG-GOV-06; AIG-OPS-01; governance minutes | Draft | Not measured | 0% |  | Validate the decision thresholds, exception route, approval authority and reporting frequency.
OBJ-03 | Identify and manage impacts on residents, staff, communities and protected or vulnerable groups. | Material privacy, equality, human-rights, safeguarding and societal impacts are assessed and treated before approval and monitored in use. | ISO 6.2; A.5.2-A.5.5; A.8.2-A.8.5 | R-06, R-07, R-08, R-13 | Percentage of cases triggering DPIA, Equality Impact Assessment, Human Rights Assessment or Responsible AI Assessment completed, approved and linked to the AI Register. | Not established — assessment population and baseline required. | Proposed: 100% of triggered assessments completed before approval; all material actions assigned and tracked to closure. |  | Service Owner / AI Governance Lead | DPO; Equality and Human Rights Leads; Legal; Safeguarding; Communications | At intake, before approval and on material change | AIG-ASS-04 to AIG-ASS-07; AIG-DEC-03; AIG-OPS-05; action records | Draft | Not measured | 0% |  | Confirm assessment triggers, specialist sign-off rules, action ownership and evidence retention.
OBJ-04 | Assure data, technical, security and operational readiness for production AI. | AI systems operate within approved data, performance, resilience, security and change-control parameters. | ISO 6.2, 8.1; A.4.2-A.4.6; A.6.2.2-A.6.2.8; A.7.2-A.7.6 | R-07, R-10, R-11, R-15 | Percentage of production systems with approved data controls, verification/validation, security review, deployment plan, monitoring thresholds and rollback or exit arrangements. | Not established — production-system baseline required. | Proposed: 100% of production systems meet the applicable readiness set; zero unresolved critical security or validation finding at go-live. |  | Service Owner / AI Technical Lead | Data Owner; Security; Architecture; Information Governance; Supplier Owner | Before go-live; monthly or risk-based operational review | AIG-ASS-02; AIG-ASS-09; AIG-ASS-11; AIG-OPS-01; test and monitoring evidence | Draft | Not measured | 0% |  | Agree the minimum readiness set by risk tier and establish evidence owners for each live system.
OBJ-05 | Provide effective human oversight, transparency, challenge and redress. | People affected by Council AI can understand relevant use, obtain appropriate human consideration and raise concerns safely. | ISO 6.2; A.5.4; A.8.2-A.8.5; A.9.2-A.9.4 | R-08, R-12 | Percentage of applicable systems with tested human-oversight and override arrangements, accessible user information, complaint routes and response monitoring. | Not established — applicability and baseline review required. | Proposed: 100% of applicable systems; all material complaints and oversight failures investigated and actioned within approved timescales. |  | Service Owner / Communications | AI Governance Lead; Complaints; Legal; Equality; Frontline Teams | Before go-live; quarterly and after material complaint or incident | AIG-ASS-09; AIG-ASS-10; AIG-OPS-05; AIG-OPS-03; user testing and complaint records | Draft | Not measured | 0% |  | Define applicability, accessibility standards, service-response times and oversight-effectiveness measures.
OBJ-06 | Control AI supplier, partner and shared-service dependencies. | Third-party AI responsibilities, evidence, change, incident, resilience and exit obligations are understood and enforceable. | ISO 6.2; A.10.2-A.10.4 | R-09, R-10, R-15 | Percentage of material AI suppliers with completed due diligence, approved contractual controls, evidence access, change notification, incident support and exit plan. | Not established — contract and supplier baseline required. | Proposed: 100% before contract, renewal or material change; all critical supplier gaps resolved or formally accepted. |  | Procurement / Service Owner | Legal; Security; DPO; AI Governance Lead; Commercial and Contract Owners | At procurement, renewal and material supplier change; quarterly portfolio review | AIG-ASS-08; AIG-ASS-11; contracts; supplier review and assurance records | Draft | Not measured | 0% |  | Confirm the material-supplier population, mandatory clauses, acceptance authority and assurance cadence.
OBJ-07 | Detect, respond to and learn from AI incidents, concerns, performance deterioration and control failures. | Potential harm is contained promptly and recurring causes drive corrective action and control improvement. | ISO 6.2, 9.1, 10.1-10.2; A.3.3; A.6.2.6-A.6.2.8; A.8.3-A.8.4 | R-11, R-12, R-14 | Percentage of AI incidents and material control exceptions triaged within approved timescale, root-caused where required and closed with effectiveness evidence. | Not established — incident taxonomy and baseline required. | Proposed: 100% triaged within approved severity timescales; 100% material corrective actions tracked to verified closure. |  | Incident Lead / AI Governance Lead | Service Owners; Security; DPO; Legal; Complaints; Communications | Per incident; monthly trend review; quarterly governance review | AIG-OPS-05; AIG-OPS-06; AIG-OPS-03; incident, action and lessons-learned records | Draft | Not measured | 0% |  | Align severity, notification, escalation, investigation and effectiveness criteria with Council incident processes.
OBJ-08 | Establish an effective, competent and continually improving AIMS. | The management system is approved, resourced, audited, reviewed and improved on evidence rather than policy intent alone. | ISO 5-10; A.2.2-A.2.4; A.3.2; A.4.6 | R-01, R-04, R-05, R-13, R-14 | Completion of approved AIMS programme, role-based competence, internal audit, management review and improvement actions by agreed dates. | Design suite exists; operational baseline and effectiveness evidence not established. | Proposed: all governance roles appointed and trained; annual internal audit and management review completed; 100% critical/high actions closed by target or formally escalated. |  | Executive Sponsor / AI Governance Lead | AI Assurance Board; Internal Audit; HR/L&D; Legal; Risk; all control owners | Monthly implementation review; at least annual audit and management review | AIG-GOV-02; AIG-OPS-05; AIG-OPS-06; AIG-GOV-06; AIG-AIMS-01 to AIG-AIMS-03; audit and review records | Draft | Not measured | 0% |  | Approve the AIMS programme, resources, competence plan, audit programme and management-review calendar.

## Risk Treatment
The Council — AIMS Risk Treatment Plan
AIG-AIMS-03 · v1.2 draft · Draft for Council review · OFFICIAL
Purpose: maintain AIMS-level risks, provisional inherent assessment, proposed treatment, ownership, evidence and residual-risk review.
Current position: scores and treatments are a desk-review starting point only. Validate them in a Council risk workshop and do not enter a control-effectiveness (CE) score until treatment implementation and evidence have been reviewed. Residual score = inherent score × CE factor (CE ÷ 5), per Playbook §4.4.3; the effective tier stays at the inherent tier until controls are evidenced, and a reduction from High or Critical also needs independent verification.
Risk ID | Risk scenario | Cause / current gap | Potential consequence | Source | ISO / Annex A links | Inherent likelihood | Inherent impact | Inherent score | Inherent rating | Treatment option | Treatment / control action | Proposed owner | Status | Target date | Control effectiveness (CE 1-5; 1 very strong, 5 ineffective) | CE factor (CE ÷ 5) | Residual score | Residual rating | Related objective(s) | SoA control links | Evidence / record | Review trigger | Record QA
R-01 | The AIMS remains unapproved or is treated as operational before formal adoption. | Scope, policy, authority, objectives and control decisions are still draft. | Unclear accountability, inconsistent decisions, unsupported conformity claims and inability to demonstrate effective governance. | Suite QA; AIG-AIMS-01 and AIG-AIMS-02 draft status | ISO 4.4, 5.1-5.3, 6.2; A.2.2-A.2.4 | 4 | 5 |  |  | Modify | Confirm adopting authority and accountable owner; approve scope, policy, objectives, risk criteria and SoA; communicate effective date and transition plan. | Executive Sponsor / AI Governance Lead | Treatment planned | [5 empty] | OBJ-02, OBJ-08 | A.2.2-A.2.4; A.3.2 | Approval, communication and controlled-document records | Change in leadership, delegations, scope or certification intent
R-02 | AI activity is omitted from the inventory, including embedded, pilot, supplier or shadow AI. | Distributed ownership and inconsistent discovery, registration and procurement triggers. | Unassessed systems may process data or affect services without ownership, controls, monitoring or approval. | AIG-AIMS-01 internal context; inventory completeness not evidenced | ISO 4.1, 6.1, 8.1; A.4.2; A.9.2 | 4 | 5 |  |  | Modify | Run a Council-wide inventory baseline and shadow-AI campaign; integrate registration triggers into procurement, digital delivery, security and data processes; test completeness periodically. | AI Governance Lead / Service Owners | Treatment planned | [5 empty] | OBJ-01 | A.4.2; A.8.5; A.9.2 | AI Register, discovery results, reconciliation and exception records | New service, procurement, embedded feature or audit finding
R-03 | Governance evidence and decisions become fragmented across boards, tools and lifecycle stages. | Multiple approval interfaces and inconsistent use of a single AI Register ID and evidence links. | Conditions, actions or material facts may be lost, duplicated or contradicted, allowing premature deployment or weak auditability. | AIG-AIMS-01 distributed ownership/evidence context | ISO 7.5, 8.1, 9.1; A.6.2.3; A.8.5 | 4 | 4 |  |  | Modify | Mandate one AI Register ID, controlled decision record and evidence index across all gates; define hand-offs, action closure and register-update accountability. | AI Governance Lead / Governance Secretariat | Treatment planned | [5 empty] | OBJ-01, OBJ-02 | A.3.2; A.6.2.3; A.8.5 | Register audit trail, decision records, minutes and evidence links | Any gate transfer, ownership change, material condition or audit exception
R-04 | Roles, delegations or approval authorities are unclear or conflict with Council governance. | Proposed governance bodies and responsibilities have not been formally appointed and aligned to delegations. | Decisions may lack authority; specialist accountability may be bypassed; escalation and ownership may fail. | AIG-GOV-06 and AIG-AIMS-01 adoption decisions pending | ISO 5.3, 7.1; A.3.2 | 3 | 5 |  |  | Modify | Approve Terms of Reference, delegations, membership, deputies, conflicts process and RACI interfaces; retain appointment and decision-authority evidence. | Executive Sponsor / Monitoring Officer | Treatment planned | [5 empty] | OBJ-02, OBJ-08 | A.3.2; A.10.2 | Approved governance documents, appointments and delegations | Organisational restructure, delegation change or disputed decision
R-05 | Insufficient competence or capacity causes inconsistent AI governance and control operation. | Variable AI literacy and limited specialist capacity across services and assurance functions. | Risk signals may be missed, documentation may be poor and governance may create delay or unsafe shortcuts. | AIG-AIMS-01 capability and capacity issue | ISO 7.1-7.3; A.4.6 | 4 | 4 |  |  | Modify | Complete role-to-competence mapping, resource plan, role-based training and effectiveness checks; establish specialist escalation and succession arrangements. | AI Governance Lead / HR-L&D | Treatment planned | [5 empty] | OBJ-08 | A.3.2; A.4.6 | Competence matrix, training records, assessments and resource decisions | New role, control failure, audit finding or material workload change
R-06 | Material impacts on people or communities are not identified or treated before use. | Impact assessment triggers, participation and specialist reviews are not consistently applied to live cases. | Unfair, unlawful, inaccessible or harmful outcomes and weakened public trust or legal defensibility. | AIG-ASS-04 to AIG-ASS-07 are controlled templates; live application not yet evidenced | ISO 6.1, 8.1; A.5.2-A.5.5 | 3 | 5 |  |  | Modify | Validate assessment triggers; complete and approve assessments for priority systems; engage affected groups proportionately; track mitigations and residual-risk acceptance. | Service Owner / AI Governance Lead | Treatment planned | [5 empty] | OBJ-03 | A.5.2-A.5.5; A.8.3-A.8.5 | Approved assessments, engagement, decisions and action closure | New affected group, complaint, material change or adverse outcome
R-07 | Poor data quality, provenance, representativeness or preparation undermines AI outcomes. | System-level data controls and evidence have not been validated across live systems. | Inaccurate, biased or unreliable outputs; inability to reproduce decisions or investigate incidents. | AIG-ASS-02, AIG-ASS-05 and AIG-ASS-09 design controls; operational evidence required | ISO 6.1, 8.1; A.7.2-A.7.6 | 4 | 4 |  |  | Modify | Create dataset inventories and data-management plans; set measurable quality and representativeness criteria; retain provenance, preparation, approval and monitoring evidence. | Data Owner / Service Owner | Treatment planned | [5 empty] | OBJ-03, OBJ-04 | A.4.3; A.7.2-A.7.6 | Dataset records, tests, lineage, exceptions and monitoring | Dataset, purpose, population, supplier or preparation change
R-08 | Human oversight, transparency, challenge or redress is ineffective. | Oversight design, instructions and public information may be generic or untested. | People may be unable to understand, contest or correct AI-supported decisions; harmful automation bias may persist. | AIG-ASS-09, AIG-ASS-10 and AIG-OPS-03 require live validation | ISO 6.1, 8.1; A.5.4; A.8.2-A.8.5; A.9.2-A.9.4 | 3 | 5 |  |  | Modify | Define and test oversight, pause/override and escalation; publish accessible information; integrate complaints and redress; monitor oversight use and effectiveness. | Service Owner / Communications | Treatment planned | [5 empty] | OBJ-03, OBJ-05 | A.5.4; A.8.2-A.8.5; A.9.2-A.9.4 | User tests, oversight logs, complaints, decisions and corrections | Complaint, override failure, user research or material service change
R-09 | Supplier or partner dependencies are accepted without sufficient assurance or enforceable obligations. | Due diligence, contracts and evidence access have not been tested consistently on material live suppliers. | Hidden model/data risks, unnotified change, delayed incident support, lock-in or ineffective exit. | AIG-ASS-08 and AIG-ASS-11 design controls; supplier baseline required | ISO 6.1, 8.1; A.10.2-A.10.4 | 4 | 4 |  |  | Modify | Baseline material suppliers; apply due diligence and mandatory contract controls; set review cadence, evidence rights, change/incident notification, resilience and exit obligations. | Procurement / Service Owner | Treatment planned | [5 empty] | OBJ-06 | A.10.2-A.10.4; A.4.4-A.4.5 | Due diligence, contracts, assurance reviews and exit tests | Procurement, renewal, supplier change, incident or performance failure
R-10 | AI security, privacy or misuse controls are inadequate for the system and threat context. | AI-specific threat modelling, access, logging and supplier controls are not evidenced for all priority systems. | Data leakage, manipulation, unauthorised use, service disruption, compromised outputs or regulatory breach. | AIG-ASS-11 controlled checklist; live security evidence required | ISO 6.1, 8.1; A.4.4-A.4.5; A.6.2.4-A.6.2.8 | 3 | 5 |  |  | Modify | Perform risk-tiered security and privacy reviews; define technical controls, abuse testing, logging, vulnerability handling and go-live closure criteria. | Security Lead / Service Owner | Treatment planned | [5 empty] | OBJ-04, OBJ-06 | A.4.4-A.4.5; A.6.2.4-A.6.2.8; A.10.3 | Threat model, test results, security decision and monitoring | Threat, vulnerability, architecture, model or hosting change
R-11 | Performance deterioration, drift or material change is not detected and reassessed. | Operational thresholds, ownership and material-change triggers are not yet operating across the portfolio. | Systems may remain in use outside approved performance, risk, purpose or data conditions. | AIG-OPS-05, AIG-OPS-06 and AIG-OPS-01 require live monitoring records | ISO 8.1, 9.1; A.6.2.6-A.6.2.8 | 4 | 4 |  |  | Modify | Approve system monitoring plans and thresholds; assign review owners; connect alerts and material changes to pause, investigation, reapproval and register update. | System Owner / Service Owner | Treatment planned | [5 empty] | OBJ-04, OBJ-07 | A.6.2.6-A.6.2.8; A.8.4 | Monitoring logs, alerts, reviews, changes and reapproval | Threshold breach, drift, supplier update or scope change
R-12 | AI incidents, complaints or concerns are not escalated, investigated or converted into corrective action. | Reporting routes and incident workflow have not been exercised end to end. | Continuing harm, missed notification, repeated failures and loss of trust or learning. | AIG-OPS-03 design form; exercise and live records required | ISO 7.4, 10.1-10.2; A.3.3; A.8.3-A.8.4 | 3 | 5 |  |  | Modify | Align incident taxonomy and routes; run a tabletop exercise; confirm authority, communications and notifications; track root cause, corrective action and effectiveness. | Incident Lead / AI Governance Lead | Treatment planned | [5 empty] | OBJ-05, OBJ-07 | A.3.3; A.8.3-A.8.4 | Exercise report, incident records, actions and effectiveness checks | Incident, complaint, near miss, control failure or external report
R-13 | Applicable legal, regulatory, contractual or Council requirements are incomplete or outdated. | No single validated AIMS obligations and change record has yet been evidenced. | Controls and decisions may rely on obsolete or incomplete requirements, creating non-compliance or rework. | AIG-AIMS-01 section 8 requires a controlled requirements record | ISO 4.2, 6.1, 9.1; A.2.3; A.8.5 | 3 | 5 |  |  | Modify | Establish the AIMS applicable-requirements register with authoritative owners, sources, applicability, affected controls, review dates and change assessment. | Legal Services / AI Governance Lead | Treatment planned | [5 empty] | OBJ-03, OBJ-08 | A.2.3; A.8.5; A.10.2-A.10.4 | Requirements register, legal review and change records | Legal, regulatory, policy, contract or service change
R-14 | The Council cannot demonstrate AIMS effectiveness because internal audit and management review are not operating. | Current evidence is primarily controlled design documentation rather than sampled operational records. | Weak assurance, recurring gaps and unsupported certification or leadership claims. | AIG-AIMS-02 shows zero controls implemented/evidenced/effective | ISO 9.1-9.3, 10.1-10.2 | 4 | 4 |  |  | Modify | Approve audit and management-review programmes; define evidence thresholds; conduct the first cycle; track findings, corrective actions and effectiveness. | AI Assurance Board / Internal Audit | Treatment planned | [5 empty] | OBJ-07, OBJ-08 | A.2.4; A.5.3; A.6.2.3 | Audit reports, management review, actions and verified closure | Audit plan, management review, major incident or recurring finding
R-15 | AI systems or supplier dependencies are retired or exited without controlled records, continuity or data handling. | Retirement, archival, replacement and supplier-exit controls are not evidenced across real systems. | Service disruption, retained access/data, lost audit trail, unmanaged dependency or re-emergence of retired use. | AIG-OPS-01 deployment and live-control design; exit evidence required | ISO 8.1; A.4.2-A.4.5; A.6.2.3; A.10.2-A.10.3 | 3 | 4 |  |  | Modify | Define decommissioning and exit criteria; revoke access, manage data/records, update the AI Register, validate replacement/continuity and retain closure evidence. | Service Owner / Technology Owner | Treatment planned | [5 empty] | OBJ-04, OBJ-06 | A.4.2-A.4.5; A.6.2.3; A.10.2-A.10.3 | Retirement plan, access/data closure, register and contract records | Retirement decision, supplier exit, replacement or service transfer

## Opportunities
The Council — AIMS Opportunities Register
AIG-AIMS-03 · v1.2 draft · Draft for Council review · OFFICIAL
Purpose: record opportunities that can improve AIMS effectiveness, efficiency, integration and public value.
Current position: these opportunities are proposed for evaluation. Benefits, resources, owners and dates must be approved before commitment.
Opportunity ID | Opportunity | Expected benefit | Enablement / action | Related objective(s) | ISO / SoA links | Proposed owner | Priority | Status | Target date | Evidence / indicator | Review trigger | Record QA
OPP-01 | Use one AI Register ID as the continuous governance thread across every lifecycle stage and board. | Less fragmentation, faster evidence retrieval, clearer ownership and safer hand-offs. | Mandate the identifier in intake, assessments, contracts, decision records, deployment, monitoring, incidents and reporting; test completeness. | OBJ-01, OBJ-02 | ISO 6.1, 7.5, 8.1 | AI Governance Lead | High | Proposed |  | Cross-artefact linkage rate; missing-link exceptions; audit retrieval time | Pilot completion, register change or governance-interface review
OPP-02 | Integrate AIMS controls into existing digital, data, procurement, security, legal and service-management processes. | Reduced duplication, earlier specialist involvement and a governance route that teams can use in practice. | Map control triggers and hand-offs into existing methods, gates and systems; retain specialist authority and measure cycle time and rework. | OBJ-02, OBJ-08 | ISO 4.4, 8.1 | Executive Sponsor / AI Governance Lead | High | Proposed |  | Process integration map; cycle time; late-review exceptions; stakeholder feedback | Process redesign, audit finding or repeated delay
OPP-03 | Turn the AI Register and dashboard into an evidence-led portfolio view. | Earlier identification of systemic risk, trends, capacity constraints and improvement priorities. | Define data-quality rules and automated or controlled feeds for risk, status, incidents, actions, assurance, training and benefits. | OBJ-01, OBJ-07, OBJ-08 | ISO 9.1-9.3 | AI Governance Lead / Data Owner | Medium | Proposed |  | Dashboard completeness, timeliness, exception rate and decisions supported | Reporting cycle, data-quality failure or management review
OPP-04 | Create reusable supplier assurance patterns and evidence requirements. | More consistent procurement decisions, stronger leverage, less duplicated review and better exit readiness. | Develop risk-tiered clauses, evidence packs, review cadence and exception routes using AIG-ASS-08 and AIG-ASS-11; pilot on material procurements. | OBJ-06 | ISO 8.1; A.10.2-A.10.4 | Procurement / Legal Services | High | Proposed |  | Supplier review completion, clause exceptions, assurance findings and renewal outcomes | Procurement pipeline, renewal, material supplier change or incident
OPP-05 | Use transparent governance and accessible engagement to strengthen resident and staff trust. | Better service design, earlier discovery of unintended impacts and more defensible public decisions. | Build user research, affected-group engagement, transparency and feedback into high-impact cases and monitor resulting changes. | OBJ-03, OBJ-05 | ISO 4.2, 6.1, 9.1; A.5.4; A.8.2-A.8.5 | Service Owner / Communications | Medium | Proposed |  | Engagement coverage, accessibility findings, complaints, trust feedback and design changes | New high-impact case, complaint trend or public-interest concern

## Improvement Plan
The Council — AIMS Improvement and Implementation Plan
AIG-AIMS-03 · v1.2 draft · Draft for Council review · OFFICIAL
Purpose: control the actions required to move the AIMS from documented design to approved, operating and evidenced practice.
Current position: all actions are proposed; none has started (IMP-17 is planned). Council governance must confirm sequencing, owners, resources, target dates, dependencies and acceptance evidence.
Action ID | Improvement / implementation action | Rationale / source | Related risk(s) | Related objective(s) | ISO / SoA links | Acceptance criteria / evidence | Proposed owner | Supporting roles | Priority | Status | Planned start | Target completion | Progress % | Dependency | Evidence location | Closure validation | Last reviewed | RAG | Record QA
IMP-01 | Confirm the senior accountable owner, adopting authority and formal AIMS scope. | AIG-AIMS-01 adoption decisions remain pending. | R-01, R-04 | OBJ-08 | ISO 4.3-4.4, 5.1-5.3 | Approved AIG-AIMS-01; named accountable owner; approval evidence; effective date and communicated boundary. | Executive Sponsor | AI Governance Lead; Monitoring Officer; Legal | Critical | Not started |  |  | 0% | Council delegations and governance route confirmed
IMP-02 | Validate and approve all Statement of Applicability decisions. | AIG-AIMS-02 contains 38 proposed applicable controls but no operational evidence. | R-01, R-14 | OBJ-08 | ISO 6.1; Annex A | Licensed-standard validation; approved applicability and owners; justified exclusions if any; controlled approval record. | AI Governance Lead | Control Owners; Legal; Internal Audit | Critical | Not started |  |  | 0% | IMP-01 and approved risk criteria
IMP-03 | Approve the AI policy, AIMS objectives, risk criteria and acceptance authority. | Policy and measurable management-system objectives require leadership approval and resources. | R-01, R-04 | OBJ-01 to OBJ-08 | ISO 5.2, 6.1-6.2 | Approved policy and objectives; baselines, targets, owners, dates, reporting cadence and risk-acceptance authority recorded. | Executive Sponsor / AI Assurance Board | AI Governance Lead; Risk; Finance; Service Owners | Critical | Not started |  |  | 0% | IMP-01; strategic and resource decisions
IMP-04 | Establish the controlled AIMS applicable-requirements and change register. | AIG-AIMS-01 requires a validated obligations record. | R-13 | OBJ-03, OBJ-08 | ISO 4.2, 6.1, 9.1; A.2.3 | Requirements have authoritative source, owner, applicability, affected process/control, review date, change status and evidence. | Legal Services / AI Governance Lead | DPO; IG; Equality; Procurement; Security | High | Not started |  |  | 0% | IMP-01 and confirmed scope
IMP-05 | Approve governance Terms of Reference, delegations, RACI and competence/resource plan. | Proposed governance bodies and roles need formal authority and capability. | R-04, R-05 | OBJ-02, OBJ-08 | ISO 5.3, 7.1-7.3; A.3.2; A.4.6 | Approved roles, membership, deputies, conflicts, delegations and escalation; competence matrix and resourcing decisions retained. | Executive Sponsor / AI Governance Lead | HR-L&D; Monitoring Officer; Governance Bodies | Critical | Not started |  |  | 0% | IMP-01 and organisational design
IMP-06 | Complete an AI inventory baseline and shadow-AI discovery campaign. | Inventory completeness has not been evidenced. | R-02, R-03 | OBJ-01 | ISO 6.1, 8.1; A.4.2; A.9.2 | Directorate attestations, procurement and technology reconciliations, discovered cases registered/contained, completeness result and actions approved. | AI Governance Lead | Service Owners; Digital; Procurement; Security; Data | Critical | Not started |  |  | 0% | IMP-05 roles and communications
IMP-07 | Pilot the complete governance lifecycle on representative real AI cases. | Controlled templates require operational validation and process learning. | R-03, R-06, R-10 | OBJ-02, OBJ-03, OBJ-04 | ISO 8.1; Annex A lifecycle controls | At least three cases spanning different risk tiers follow intake through decision and live/closure status; timing, rework, gaps and user feedback recorded. | AI Governance Lead / Service Owners | All applicable control functions and governance bodies | High | Not started |  |  | 0% | IMP-03 to IMP-06; suitable live cases
IMP-08 | Implement a controlled AIMS evidence repository, document-control and retention structure. | Design documents exist, but live evidence locations and retention controls are not populated. | R-03, R-14, R-15 | OBJ-01, OBJ-08 | ISO 7.5, 9.1-9.3, 10.2 | Approved taxonomy, access, versioning, retention, disposal and evidence-index rules; sampled records retrievable by AI Register ID and control. | AI Governance Lead / Information Governance | Records Management; Security; Control Owners | High | Not started |  |  | 0% | IMP-01 and corporate records requirements
IMP-09 | Deliver role-based AI governance training and verify competence. | Capability and capacity are material implementation risks. | R-05 | OBJ-08 | ISO 7.2-7.3; A.4.6 | Target populations and competencies defined; training completed; assessment/effectiveness results and remedial actions retained. | AI Governance Lead / HR-L&D | Service Owners; Specialist Control Functions | High | Not started |  |  | 0% | IMP-05 competence matrix and resource plan
IMP-10 | Apply supplier due diligence and contract controls to material live procurements or renewals. | Supplier controls need operational proof and refinement. | R-09, R-10, R-15 | OBJ-06 | ISO 8.1; A.10.2-A.10.4 | At least two material supplier cases evidence due diligence, risk-tiered terms, exceptions, assurance rights, change/incident duties and exit arrangements. | Procurement / Service Owners | Legal; Security; DPO; AI Governance Lead | High | Not started |  |  | 0% | Procurement pipeline and IMP-04 requirements
IMP-11 | Complete live impact, data, security and technical assurance for priority systems. | System-level evidence is needed to move controls beyond designed status. | R-06, R-07, R-08, R-10 | OBJ-03, OBJ-04, OBJ-05 | ISO 8.1; A.5-A.9 | Priority systems have approved assessments, data plans, test results, security decisions, oversight/transparency controls and action closure. | Service Owners | DPO; Equality; Human Rights; Data; Security; Technical Reviewers | High | Not started |  |  | 0% | IMP-06 inventory and risk prioritisation
IMP-12 | Establish operational monitoring plans and AI dashboard data-quality rules. | Monitoring and dashboard artefacts require owners, thresholds and reliable live data. | R-11, R-14 | OBJ-01, OBJ-04, OBJ-07 | ISO 9.1; A.6.2.6-A.6.2.8 | Live systems have approved measures, thresholds, owners, review cadence and change triggers; dashboard fields reconcile to source evidence. | AI Governance Lead / System Owners | Data Owner; Service Managers; Assurance Functions | High | Not started |  |  | 0% | IMP-06 inventory and IMP-11 system assurance
IMP-13 | Exercise AI incident, concern, complaint, escalation and corrective-action processes. | The incident form and routes require end-to-end testing. | R-08, R-12 | OBJ-05, OBJ-07 | ISO 7.4, 10.2; A.3.3; A.8.3-A.8.4 | Tabletop exercise completed; roles, notification, communications, evidence, root cause, action and effectiveness gaps assigned and closed. | Incident Lead / AI Governance Lead | Security; DPO; Legal; Complaints; Communications; Service Owners | High | Not started |  |  | 0% | IMP-05 roles and corporate incident interfaces
IMP-14 | Approve the AIMS internal audit programme and conduct the first audit. | No evidence yet demonstrates independent sampling of AIMS operation. | R-14 | OBJ-08 | ISO 9.2 | Risk-based audit programme, competence and independence confirmed; first audit completed; findings owned, dated and tracked. | Head of Internal Audit | AI Governance Lead; Control Owners | High | Not started |  |  | 0% | Sufficient operating evidence from IMP-07 to IMP-13
IMP-15 | Conduct the first formal AIMS management review and approve the improvement backlog. | Leadership review is required to evaluate suitability, adequacy and effectiveness. | R-01, R-14 | OBJ-08 | ISO 9.3, 10.1-10.2 | Required inputs reviewed; decisions on resources, risks, objectives, scope, SoA and improvements recorded; actions tracked. | Executive Sponsor / AI Assurance Board | AI Governance Lead; Internal Audit; Control Owners | Critical | Not started |  |  | 0% | IMP-14 audit and objective/performance evidence
IMP-16 | Validate controlled retirement, decommissioning, archival and supplier-exit arrangements. | Lifecycle closure controls need evidence from real or simulated cases. | R-15 | OBJ-04, OBJ-06 | ISO 8.1; A.4.2-A.4.5; A.6.2.3; A.10.2-A.10.3 | At least one retirement or exit test confirms decision, continuity, access revocation, data/records treatment, contract closure and AI Register status. | Service Owner / Technology Owner | Procurement; IG; Security; Data; AI Governance Lead | Medium | Not started |  |  | 0% | Suitable system or controlled simulation
IMP-17 | Societal impact assessment (ISO/IEC 42001 A.5.5): add a societal-impact prompt to the Responsible AI Assessment (AIG-ASS-04) and assess societal impacts for priority AI uses. | AIG-AIMS-11 known limitation: societal impacts (A.5.5) are not yet assessed explicitly for each use. | R-06 | OBJ-03 | ISO 6.1.4, 8.4; A.5.5 | Societal-impact prompt approved in AIG-ASS-04; priority uses assessed for societal impacts with outcomes and treatment recorded; A.5.5 entry in AIG-AIMS-02 updated. | AI Governance Lead | Service Owners; Equality; Human Rights; Legal; Communities | Medium | Planned | 2027-01-04 | 2027-03-31 | 0% | IMP-11 system assurance; AIG-AIMS-11 coverage mapping

## Lists & Guidance
AIG-AIMS-03 — Status Definitions, Risk Matrix and Use Guidance
Objective status | Meaning |  | Risk status | Meaning |  | Action status | Meaning
Draft | Proposed objective; not yet approved as a Council commitment. |  | Draft assessment | Risk description or scoring awaits validation. |  | Not started | Action is proposed and not authorised or scheduled.
Approved | Objective, owner, measure, baseline, target, resources and date are authorised. |  | Open | Risk is confirmed and requires a decision or treatment. |  | Planned | Owner and target date are confirmed.
Active | The objective is being pursued and monitored. |  | Treatment planned | Treatment is selected but not yet operating. |  | In progress | Work is actively under way.
At risk | Evidence indicates the target may not be met without intervention. |  | In progress | Treatment action is under way. |  | Blocked | A dependency or decision prevents progress and requires escalation.
Achieved | The target is met and supporting evidence has been reviewed. |  | Accepted | Authorised risk owner has accepted residual risk with review conditions. |  | Complete | Acceptance criteria, evidence and independent closure validation are complete.
Paused | Progress is formally paused with reason, authority and review date. |  | Monitoring | Treatment is operating and residual risk/effectiveness is under review. |  | Cancelled | Action is withdrawn through an authorised, recorded decision.
Closed | Objective is retired or replaced through an approved decision. |  | Closed | Risk no longer applies or is controlled within approved criteria, with evidence.
Risk scoring matrix — likelihood × impact | [5 empty] | Rating | Score
Likelihood / Impact | 1 | 2 | 3 | 4 | 5 | Low | 1-5
1 | 1 | 2 | 3 | 4 | 5 | Medium | 6-10
2 | 2 | 4 | 6 | 8 | 10 | High | 11-15
3 | 3 | 6 | 9 | 12 | 15 | Critical | 16-25
4 | 4 | 8 | 12 | 16 | 20
5 | 5 | 10 | 15 | 20 | 25
Likelihood scale
1 | Rare | Unlikely except in exceptional circumstances — Council to validate criteria.
2 | Unlikely | Could occur but is not expected — Council to validate criteria.
3 | Possible | Might occur during the planning horizon — Council to validate criteria.
4 | Likely | Expected to occur in several circumstances — Council to validate criteria.
5 | Almost certain | Expected frequently or already evident — Council to validate criteria.
Impact scale
1 | Minimal | Limited effect; routine local correction — Council to validate criteria.
2 | Minor | Contained disruption or reversible limited impact — Council to validate criteria.
3 | Moderate | Material service, legal, financial or trust impact — Council to validate criteria.
4 | Major | Serious or widespread impact requiring senior response — Council to validate criteria.
5 | Severe | Potential grave, systemic or irreversible harm — Council to validate criteria.
Decision and evidence rules
• This workbook is an AIMS-level control document; system-specific risks remain in AIG-ASS-02 and link back through the AI Register ID.
• Objective approval requires a baseline, target, owner, resources, target date, monitoring method and evidence source.
• Inherent scores are provisional desk-review judgements. Validate them against the Council’s adopted corporate risk criteria.
• Do not enter a control-effectiveness score until treatment is implemented and evidence has been reviewed. Residual score = inherent score × CE factor (CE 1–5 ÷ 5), as in Playbook §4.4.3; residual bands use the same thresholds (Low ≤5, Medium >5–10, High >10–15, Critical >15) and the effective tier stays at the inherent tier until controls are evidenced; acceptance requires authorised ownership and review conditions.
• A treatment or improvement action is complete only when acceptance criteria, evidence and closure validation are recorded.
• Update objectives, risks and actions after incidents, complaints, audit findings, management review, material change or new requirements.
• AIG-AIMS-02 references show control design coverage only; they do not prove implementation or effectiveness.
• Validate all ISO clause and control references against the Council’s licensed copy before formal adoption or certification use.
• Improvement Plan RAG: Red = Blocked, or past target date and not Complete/Cancelled; Amber = In progress, due within 30 days, or Complete without closure evidence; Green = Complete with Record QA complete; Blue = Planned; Grey = Not started or Cancelled.
Source and controlled-use note
Standard baseline: ISO/IEC 42001:2023, Information technology — Artificial intelligence — Management system.
Official standard page: https://www.iso.org/standard/42001
Council design sources: AI Governance Playbook (AIG-GOV-02, current controlled version per AIG-GOV-03); AIG-AIMS-01 AIMS Scope, Context and Interested Parties; AIG-AIMS-02 Statement of Applicability; the controlled AIG-* artefacts listed in the Artefact Index (AIG-GOV-03).
Control status: draft for Council review. Nothing in this workbook authorises deployment, accepts risk or establishes conformity.

## INTEGRATION INV-04 DEC-04
AIG-AIMS-03 — PROPOSED AIG-INV-04/AIG-DEC-04 INTEGRATION NOTES
NOT APPROVED — additive integration annex only; existing workbook content and formulas are retained unchanged. AIG-INV-04 (AI Register) and AIG-DEC-04 (Gate Log) are themselves proposed designs: until the Council approves their adoption and migration, the Council’s existing records remain authoritative and the AIG-INV-04/AIG-DEC-04 joins below are design references only. No live system, event, evidence, approval or Council decision is asserted.
Review topic | Targeted proposed integration note
Status / measurement rule | All OBJ, risk, opportunity and improvement entries remain proposed. Do not populate baseline, actual progress, residual rating, acceptance, target, resource commitment or closure from the proposed AIG-INV-04/AIG-DEC-04 design or from example data; agree measurement definitions, denominators, owner, period, target and approval first.
OBJ-01 inventory completeness | For the approved scope, reconcile known in-scope activity to permanent AIR-IDs in proposed AIG-INV-04 AI Register and discovery/mapping sources. Measure missing, duplicate, ownerless or stale records against a defined discovery population; do not count only an approved-tools-only view, which intentionally excludes non-approved lifecycle items. Keep any inventory review evidence in the AIG-INV-04 Evidence index by Evidence ID and AIR-ID.
OBJ-02 approval / gate discipline | Keep scheduled gates distinct from actual decisions: AIG-DEC-04 Gate plan is a plan; AIG-DEC-04 Gate events records dated events; AIG-DEC-04 Conditions tracks per-event conditions. Link each final decision to AIG-DEC-03 or the authorised native minutes and Evidence ID. Reconcile actual approval/outcome to AIG-INV-04 current Governance Approval Status and Operational Status; a plan, proposed event, incomplete condition, or green structural QA is not approval or permission to operate.
OBJ-03 impact assessment coverage | Use the AIR-ID to connect applicability/assessment references in the AIG-INV-04 Assessment summary to the underlying DPIA/EIA/HRA/Responsible AI records and the evidence index. Record which assessments are triggered, completed/reviewed, and actions resolved; only a substantive specialist decision/evidence establishes completion. Material scope or impact change should have a dated governance event/reassessment trail.
OBJ-04 production readiness / live operation | Join the current system and owner through AIR-ID; cite the relevant deployment decision/conditions (AIG-DEC-04 Event ID, Condition IDs, AIG-DEC-03) and AIG-OPS-02 monitoring evidence. Use actual monitored values and dated evidence in their source record. A readiness pointer, design reference or blank monitoring flag is not proof of operation.
OBJ-05 oversight / transparency / redress | Where applicable, link AIR-ID to the actual oversight/transparency/complaint evidence, and to dated AIG-DEC-04 decisions/events where approval, changed conditions, pause or resumption occurred. Keep individual complaint/person data in approved source systems; the join stores only necessary IDs and evidence pointers.
OBJ-06 suppliers / dependencies | Tie each supplier/partner obligation and due-diligence evidence to AIR-ID using evidence metadata (AIG-INV-04 Evidence index); record material release/contract changes in the appropriate source change record and any actual AIG-DEC-04 gate event. Generic supplier templates or an unpopulated reference are not an implemented contract control.
OBJ-07 incidents / exceptions / learning | Link a system-specific issue to AIR-ID and its actual incident/monitoring evidence (including AIG-OPS-03/AIG-OPS-02); when it is an AIMS nonconformity, track correction, cause and effectiveness separately in AIG-AIMS-08 and reference any AIG-DEC-04 event/condition. AIMS-wide issues may have no AIR-ID. Do not create or assert incident history.
OBJ-08 and AIMS-wide actions | Keep management-system objectives, resourcing, audit, review and improvement actions at AIMS level where they are not attributable to one system. Where a measure aggregates cases, define the frozen source population and as-at date, reconcile to AIR-IDs, and retain the underlying approved evidence; AIG-INV-04/AIG-DEC-04 are proposed joins, not live portfolio data.
Risk / opportunity / improvement registers | Preserve each risk ID, inherent/residual assessment, treatment, acceptance authority and improvement action in its authoritative AIMS record. Link system-specific risks/actions to AIR-ID and evidence references; link gate conditions only where an authorised decision created a condition. Do not collapse AIMS-level risk into system fields or confuse correcting a one-off issue with corrective action.
Review and reconciliation | At the approved review cadence reconcile objectives and actions with AIG-INV-04 identity/state, actual AIG-DEC-04 event and condition history, evidence-index pointers, AIG-OPS-02 monitoring, AIG-AIMS-07 audit, AIG-AIMS-08 CAPA and AIG-AIMS-09 management-review actions. Resolve orphan IDs, mismatched current states, overdue accepted conditions and superseded/missing evidence through an authorised, documented change.

## STANDARDS SCOPE QA
PROPOSED QA INDEX — NOT APPROVED. A source reference does not establish applicability or compliance. See AIG-AIMS-05 and AIG-AIMS-13; owners must validate the current source, case-specific scope, control evidence and adopted status.
Requirement ID | Instrument / edition | Conditional scope / relevance | Source URL | Owner validation status
REQ-014 | Local Government Act 1999 (Best Value Duty) and 2024 statutory guidance | Screen the legislation and statutory guidance requirement against this artefact's actual use and record evidence/version; see the AIG-AIMS-05 Applicable Requirements entry (REQ-014) for the controlled position. | https://www.gov.uk/government/publications/best-value-standards-and-intervention-a-statutory-guide-for-best-value-authorities | Specialist validation required
REQ-040 | ISO/IEC 42001:2023 Artificial intelligence management system | Proposed management-system design mapping; licensed clause review and adoption needed. | https://www.iso.org/standard/42001 | Specialist validation required
REQ-041 | ISO/IEC 23894:2023 AI — Guidance on risk management | Voluntary risk-management guidance; proposed alignment, not statutory conformity. | https://www.iso.org/standard/77304.html | Specialist validation required

## MAP & SPLIT CONTRACT
AIG-AIMS-03 / PROPOSED THREE-ARTEFACT SOURCE CONTRACT
Status | PROPOSED INTEGRATION DESIGN ONLY. This sheet does not amend the artefact's native assessment, decision authority, data or formulas.
Role of this file | Objectives and treatment: Use official AIR-ID for system-specific actions, an AIG-DEC-04 Event/Condition ID for gate actions, and a map Edge ID only for relationship-change questions. Do not treat closure of a map gap as risk acceptance.
AIG-INV-04 source | Separate AIG-INV-04 AI Register: official AIR-ID, current position, in-file Assessment summary/Evidence index. Reconcile against authoritative AIG-INV-04 before using a copied value.
AIG-DEC-04 source | Separate AIG-DEC-04 Gate Log: prospective Gate plan, dated Gate events, event-linked Conditions. A planned gate is not a decision. A decision requires AIG-DEC-03 or approved minutes and proper delegation.
Map source | Proposed standalone Capabilities and System Map (candidate catalogue ID AIG-INV-05): UC/CAP and component relationship pointers. Edge ID is not an approval or permission; AIG-AGT-04/AIG-AGT-05 remain sources of agent scope/authority.
Data exchange | Use controlled AIR-ID across files. Where applicable reference exact Event ID, Condition ID, Evidence ID, AG-ID and Edge ID. Record source file/version/as-at with imported or quoted evidence; no live cross-workbook formula is assumed.
Change trigger | New or expanded system/tool access, or a material model, data, interface, purpose or agent change: log the map change, obtain owner reassessment and escalate to the proper AIG-DEC-04 gate/AIG-DEC-03 decision when required.
Validation before use | The INTEGRATION INV-04 DEC-04 tab in this workbook is current supporting design guidance (not historical) and holds the detailed join notes. Controlled owners must reconcile real records, validate values and formulas in Excel, and approve migration/cutover; existing Council records remain unchanged until then.