## READ ME
AIG-DEC-04 ¦ Using the separate Gate Log
Status | Draft for Council review — unpopulated design draft; not adopted policy or an operational replacement.
Plan ≠ event | Gate plan is prospective. Only a dated Gate events row says a gate occurred. A plan cannot grant approval.
Event ≠ authority | An assurance opinion or review may be logged without being an approval. Record the delegated decision-maker and authoritative AIG-DEC-03 decision or approved-minutes reference for a decision event.
Conditions | Keep each condition as its own row linked to a dated Decision event (Outcome ‘Progress with condition’, ‘Re-authorise’ or ‘Resume’); record the action, owner, due date, state, verifier/date and closure evidence or waiver authority. Overdue is derived from the due date, never typed.
Join to AIG-INV-04 | Use the same controlled AIR-ID as the AIG-INV-04 Register. There are no fragile external-workbook formulas; reconcile AIG-INV-04 current status and latest Event ID to the actual AIG-DEC-04 event and decision record.
Separate system map | The proposed standalone Capabilities and System Map links use cases, capabilities and components to controlled AIR-IDs. It is not this Gate Log, the AIG-DEC-01 governance Gate Map or an approval source. No gate is proved by a map link.
Before migration | Agree field dispositions with the owners of the Council's existing (pre-suite) gate and decision logs, split legacy multi-condition cells without losing meaning, reconcile event IDs and actual delegations, test with controlled records in Excel, approve cutover and archive sources. None were migrated here.
Priority override | A priority override is its own Event type. Record the delegated decision-maker and the AIG-DEC-03 or approved-minutes reference; the priority before and after, reason and Assurance update reference live in that record. Leave Outcome blank or No decision: an override changes governance attention, not progress through a gate.
Change 29 Sep 2026 | Added Event type “Priority override” and its row check, so the override route in AIG-ASS-01 and Playbook Annex G.4 has a controlled home.
One outcome per UC-ID | AIG-DEC-03 (or approved minutes) is the authoritative decision record, one outcome per UC-ID. Log one Gate events row per UC-ID: where one meeting decides several uses, enter a row for each (Event ID with a suffix, e.g. EVT-0012-a, EVT-0012-b) with that use's own outcome. A row listing several UC-IDs is flagged by the Row check.
Controlled lists | Gate / forum uses the AIG-DEC-01 gates on the Lists sheet (configure forum names locally). Event types include Intake / registration; outcomes include Suspend, Decommission, Re-authorise and Resume (lifts a precautionary pause; allowed only in the event straight after the pause for the same use). The Lists sheet maps each outcome to the AIG-DEC-03 outcome vocabulary and each condition state to AIG-DEC-03 and the UC-ID current view.
Evidence, source and time | Gate events carry Time, Source and Evidence ID(s) (AIG-INV-04 Evidence index) and the event-time lifecycle stage (columns R–U). Conditions carry Verified by / date and, for monitoring conditions, the AIG-OPS-02 evidence ref needed before closure.
QA change 29 Sep 2026 | Row checks added to Gate plan and strengthened on Gate events and Conditions; see Document Control.
Precautionary pause | An immediate precautionary pause (Playbook §4.7.17) does not wait for a governance decision, so it is not logged as a Decision. Use Event type “Precautionary pause (containment)” with Outcome “Paused — pending decision”, the person who applied it in Decision-maker / role, the AIG-OPS-03 incident ref (column V) and the date by which the delegated authority will decide on continued suspension, resumption or withdrawal (column W). That later decision is its own Decision event with its AIG-DEC-03 ref: Resume where the approval is unchanged, otherwise the outcome decided (see Resume after a pause). Proposed — for Council confirmation.
Change 30 Sep 2026 | v3.9.2: Gate plan duplicate check keys on AIR-ID + UC-ID scope + gate; precautionary pause event type added (Gate events columns V–W, Lists row 15, row check). See Document Control.
Screening considered (column X) | Gate events column X records whether the decision-maker saw and considered the equality, human rights and data protection screening (including any done by reference, Playbook §4.6). It must be Yes for a Decision with Outcome Progress, Progress with condition, Re-authorise or Resume; it matches the tick line in AIG-DEC-03. Proposed — for Council confirmation.
Resume after a pause | Outcome “Resume” is a Decision that lifts a precautionary pause with the use’s approval unchanged (AIG-DEC-03: Approved, or Approved with conditions where new conditions are set). Enter it as the next Gate events row for the same AIR-ID and UC-ID after the pause row; the row check flags it otherwise. Log a pause one row per affected UC-ID, so each use can be resumed separately. Where the use needs reassessment first, use Re-authorise. Proposed — for Council confirmation.
Locked row checks | The row-check columns (Gate plan M; Gate events N and Q; Conditions J) are locked with sheet protection and no password, so they cannot be typed or pasted over. Every input column stays editable, and any filter buttons still work. To sort, or to change a formula, unprotect the sheet (no password) and protect it again afterwards.
Change 3 Oct 2026 | v3.9.8: column X (screening considered), Outcome Resume (Lists row 16) and locked row-check columns. See Document Control.

## Gate plan
AIG-DEC-04 / GATE PLAN — WHAT IS EXPECTED
Prospective requirements only. A plan is not evidence that a gate happened or that a use was approved. | [9 empty] | Gate plans are prospective requirements, never approval. State whether the planned gate concerns named UC-ID(s) or a shared system baseline. The duplicate check keys on AIR-ID + UC-ID scope + gate: each use of a system has its own plan rows, and a system-level row (blank UC-ID) counts separately.
Plan ID | AIR-ID | Gate / forum | Trigger / stage | Requirement | Basis / triage ref | Target date | Responsible role | Plan state | N-A / waiver rationale and authority ref | UC-ID scope(s) (blank only for explicit system baseline) | Decision scope (UC-ID specific / Shared system baseline) | Row check

## Gate events
AIG-DEC-04 / GATE EVENTS — WHAT ACTUALLY HAPPENED
One dated occurrence per row. An assurance opinion is not a delegated approval. Decision events need the authoritative AIG-DEC-03 decision or approved-minutes reference. | [13 empty] | One dated event row per UC-ID (split multi-use decisions into suffixed Event IDs). UC-ID specific scope is mandatory for use approval; a shared baseline event is not UC approval. A precautionary pause (Playbook §4.7.17) is containment, not a decision: Event type “Precautionary pause (containment)”, Outcome “Paused — pending decision”, no AIG-DEC-03 ref needed; record the AIG-OPS-03 incident ref (V) and the follow-up decision due date (W). To lift the pause with the approval unchanged, record a Decision with Outcome “Resume” in a later row for the same AIR-ID and UC-ID (AIG-DEC-03 ref needed; new conditions go on Conditions rows).
Event ID | AIR-ID | Plan ID (if any) | Gate / forum | Event type | Date | Outcome | Decision-maker / role | AIG-DEC-03 / minutes ref | Assurance opinion ref | Technical snapshot / as-at ref | Next gate / action | Recorded by | Row check | UC-ID(s) covered by this dated event | Decision scope (UC-ID specific / Shared system baseline) | Decision-scope completeness prompt | Time (hh:mm) | Source (minutes / decision record / system) | Evidence ID(s) (AIG-INV-04 Evidence index) | Event-time lifecycle stage | Incident ref (AIG-OPS-03), precautionary pause | Follow-up decision due date (precautionary pause) | Screening considered by the decision-maker (Yes / No)

## Conditions
AIG-DEC-04 / CONDITIONS — WHAT REMAINS OPEN
One condition per row. Parent Event ID must exist in Gate events. Evidence of closure or a properly authorised waiver is required. | [9 empty] | For UC-ID-specific conditions, enter one UC-ID per row; the parent Gate events row carries one UC-ID. Shared baseline conditions have a blank UC-ID. Overdue is derived by the Row check (Open and due date passed).
Condition ID | Event ID | AIR-ID | Required action / condition | Action owner | Due date | State | Closed / waived on | Evidence / waiver authority ref | Row check | UC-ID scope (blank only if shared system condition) | Condition scope (UC-ID specific / shared system baseline) | Verified by / date | Monitoring condition? (Yes / No) | AIG-OPS-02 evidence ref (monitoring conditions)

## Lists
AIG-DEC-04 / CONTROLLED LISTS AND OUTCOME MAPPING
Controlled values used by the validations. Gate names follow the AIG-DEC-01 Gate Map (forum names configurable locally). The mapping shows how each gate outcome corresponds to the AIG-DEC-03 decision outcome used in AIG-INV-04 and the UC-ID current view.
Gate (AIG-DEC-01) | Lifecycle stage (Playbook §3.6) | Gate event Outcome (AIG-DEC-04) | AIG-DEC-03 outcome for the UC-ID | Allowed Event type
Gate 0 Intake / opportunity | Idea and Innovation | Progress | Approved | Decision
Gate 1 Strategic prioritisation | Registration and Intake | Progress with condition | Approved with conditions (≥1 Conditions row) | Decision
Gate 2 Technical design review | Risk Assessment and Review | Return for evidence | Deferred | Decision
Gate 3 Case for change / strategic alignment | Approval and Assurance | Pause | Deferred (before go-live) / Suspended (in operation) | Decision
Gate 4 Procurement | Deployment and Operation | Stop | Rejected | Decision
Gate 5 Ethics assessment | Monitoring and Review | Suspend | Suspended | Decision
Gate 6 Deployment / go-live | Retirement and Decommissioning | Decommission | Retired | Decision
Gate 7 Operate, monitor, review & change |  | Re-authorise | Approved or Approved with conditions (after reassessment) | Decision
Gate 8 Retirement / closure |  | Opinion only | None — assurance input, not a decision (Pending) | Assurance opinion / Review only
Other forum (name it in Decision-maker / role) |  | No decision (or blank) | None (Pending) | Review only / Priority override / Intake / registration
|  | Paused — pending decision | None: containment, not a decision (the UC-ID keeps its recorded AIG-DEC-03 outcome until the follow-up decision; Playbook §4.7.17) | Precautionary pause (containment)
|  | Resume | Approved or Approved with conditions: the approval in force before the precautionary pause carries over (new conditions go on Conditions rows); only in the event straight after the pause for the same AIR-ID and UC-ID | Decision
|  | Condition state (AIG-DEC-04) | AIG-DEC-03 condition state (shared list) | UC-ID current view condition state
|  | Open | Open | Open
|  | Closed-verified | Closed-verified | Closed-verified
|  | Accepted-open | Accepted-open | Accepted-open
|  | Waived | Waived | Waived
|  | Unknown | Unknown | Unknown
|  | Superseded (not a state) | Not a state: close the old condition as Waived, citing the replacing Condition ID and the authority in the evidence / waiver ref | Waived
|  | Overdue (not a state) | Derived from Open + due date before today; never typed | Open (overdue shown by the check)

## Document Control
AIG-DEC-04 — Document Control
Controlled working template. Draft for Council review; not Council-adopted and not effective until formally approved.
Field | Controlled value
Document ID | AIG-DEC-04
Artefact | AI Governance Gate Log (proposed separate design)
Version | 1.3 draft
Status | Draft for Council review
Document owner | AI Governance Lead
Approving body | Competent Council authority under Constitution and Scheme of Delegation; AI Assurance Board provides assurance where applicable
Approval date | Not yet approved
Effective date | Not yet effective
Next review date | To be set on approval: 12 months after effective date or sooner following material change
Classification | OFFICIAL
Change history
Version | Date | Change | Author / owner
1.0 draft | 29 September 2026 | First controlled version with document control. QA remediation — applied findings QA-095, QA-155, QA-189, QA-216, QA-224, QA-231, QA-232, QA-233, QA-234, QA-238, QA-251, QA-265, QA-266, QA-272, QA-291 (see QA change log). | AI Governance Lead
1.1 draft | 30 September 2026 | v3.9.2: Gate plan duplicate check now keys on AIR-ID + UC-ID scope + gate, so several uses of one system no longer raise false duplicates; a system-level row with a blank UC-ID counts separately (scenario finding W-02). Gate events: new Event type “Precautionary pause (containment)” with Outcome “Paused — pending decision”, no AIG-DEC-03 ref required, and new columns V (AIG-OPS-03 incident ref) and W (follow-up decision due date) checked by the Row check; Lists row 15 maps it to no AIG-DEC-03 outcome (containment, not a decision) (W-06). Proposed — for Council confirmation. See QA change log. | AI Governance Lead
1.2 draft | 3 October 2026 | v3.9.7: Row checks tightened so incomplete rows no longer show “Check against source”. Gate plan: Requirement and Plan state must be filled. Gate events: a linked Plan ID must match the event’s gate and (where the plan names one) its UC-ID; an Assurance opinion event needs its assurance ref; Opinion only and No decision are accepted only on the event types the Lists mapping allows; one UC-ID per row is also checked for spaces and slashes; a precautionary pause follow-up date cannot be before the pause. Conditions: state Unknown is flagged for the owner to confirm. No gate, list or column changes. Proposed, for Council confirmation. | AI Governance Lead
1.3 draft | 3 October 2026 | v3.9.8: Gate events gains column X “Screening considered by the decision-maker (Yes / No)”. The row check flags a Decision with outcome Progress, Progress with condition or Re-authorise unless X is Yes, matching the AIG-DEC-03 screening line. New Outcome “Resume” (Lists row 16): a Decision that lifts a precautionary pause with the approval unchanged; the row check accepts it only when the last earlier row for the same AIR-ID and UC-ID is the pause, and it needs X = Yes like other go-ahead outcomes. Conditions may hang off a Resume decision. The condition-state block on Lists moves down one row. The row-check columns (Gate plan M; Gate events N and Q; Conditions J) are locked with sheet protection and no password, so they cannot be typed or pasted over; every input column stays editable and any filter buttons still work; to sort, unprotect the sheet and protect it again afterwards. Proposed, for Council confirmation. | AI Governance Lead