## Summary
The Council — AIMS Roles, Competence, Awareness and Communications Plan
AIG-AIMS-04 · v1.3 draft · Draft for Council review · OFFICIAL · ISO/IEC 42001:2023
Purpose: operationalise accountable AIMS roles, required competence, learning and internal/external communications without changing Council delegations or specialist authority.
Status statement: all appointments, deputies, authority mappings, competence requirements, training modules and communications are proposed. No individual is confirmed competent, trained or authorised until the Council approves the design and retains evidence.
Document control | Controlled value |  | Role readiness |  | Competence and learning readiness
Document ID | AIG-AIMS-04 |  | Measure | Result | Measure | Result
Version | 1.3 draft |  | Defined role/body records |  | Role groups mapped
Status | Draft for Council review |  | Appointments confirmed |  | Current assessments complete
Document owner | AI Governance Lead |  | Deputies recorded |  | Open competence gaps (assessed gap / expired)
Approving authority | To be confirmed under Council delegations |  | Appointment evidence recorded |  | Learning modules designed
Effective date | Pending formal approval |  | Roles reviewed |  | Approved / active modules
Review frequency | At least annually and on material change |  | Role records QA complete |  | Average completion
Primary authority source | AIG-GOV-06 Terms of Reference; approved Council delegations prevail |  |  |  | Learning records QA complete
Implementation source | AIG-AIMS-03 IMP-05 and IMP-09
Classification | OFFICIAL |  | Communications readiness |  | Important control distinction
|  |  | Measure | Result | 1. A role description does not appoint a person.
|  |  | Communication activities |  | 2. Training completion does not by itself prove competence.
|  |  | Approved / active |  | 3. Competence does not itself confer delegated authority.
|  |  | Issued / completed |  | 4. Communication activity needs retained evidence and an effectiveness measure.
|  |  | Target dates recorded |  | 5. AIG-GOV-06 and approved Council delegations remain the authority source.
|  |  | Last-issued dates recorded |  | 6. Specialist/statutory functions retain their existing authority.
|  |  | Communication QA complete |  | 7. Draft entries must not be represented as operating controls.
Controlled implementation sequence
1. Approve the Terms of Reference, delegations, retained specialist authority and the role design in this workbook.
2. Name role holders and deputies; retain appointment, conflict and authority evidence.
3. Confirm target populations, required competency profiles, resources and assessment methods.
4. Approve learning content, delivery owners, dates, accessibility, pass criteria and LMS/evidence arrangements.
5. Assess role holders; record competence conclusions, gaps, supervised practice and remedial actions.
6. Approve and issue communications in sequence with AIMS adoption and operational rollout.
7. Review training, communication and role effectiveness using incidents, audit, performance and stakeholder feedback.
Version | Date | Change |  |  | Author / owner
1.0 draft | 2026-08-07 | Initial AIMS role-accountability, competence, learning, awareness and communications design aligned to AIG-GOV-06, AIG-OPS-01 and AIG-AIMS-03. |  |  | AI Governance Lead
1.1 draft | 28 September 2026 | Make role-accountability QA colours match exact statuses.
1.2 draft | 29 September 2026 | QA remediation — applied findings QA-218, QA-220, QA-238, QA-240, QA-241, QA-251, QA-255, QA-280, QA-282, QA-284, QA-291 and decision D2 role names (see QA change log). |  |  | AI Governance Lead
1.3 draft | 12 October 2026 | v3.9.10: Role Accountability adds ROL-20 Data Steward, who maintains data quality, lineage and the Information Asset Register link (AIG-INV-04 column AA) on behalf of the Data Owner. Summary counts extended to the new row. Proposed — for Council confirmation. |  |  | AI Governance Lead

## Role Accountability
The Council — AIMS Role Accountability and Appointment Register
AIG-AIMS-04 · v1.3 draft · Draft for Council review · OFFICIAL · ISO/IEC 42001:2023
Purpose: define proposed accountability, responsibilities, authority boundaries, interfaces, competence and appointment evidence for AIMS roles and bodies.
Current position: role descriptions are proposed design only. Complete named appointment, deputy, evidence and review fields only after formal authority is confirmed; approved Council delegations and specialist responsibilities prevail.
Role ID | Role / body | AIMS layer | Purpose / accountability | Key responsibilities | Decision / approval authority | Consultation / escalation | Named appointee | Deputy | Appointment status | Appointment evidence | Required competency level | Training pathway | Review date | Related suite references | ISO / SoA links | Role record / source | Record QA
ROL-01 | Executive Sponsor | Strategic oversight | Senior accountability, sponsorship and resources for the AIMS. | Champion responsible AI; secure adoption and resources; hold leadership to account; resolve strategic barriers; receive escalations and management-review outputs. | Sponsors formal adoption and decisions reserved under Council delegations; does not replace statutory or specialist authority. | Escalate critical matters to Executive Leadership and the AI Assurance Board; consult Monitoring Officer, SIRO, DPO and other control owners. |  |  | Proposed |  | Level 5 — AI Governance Leader | TRN-01, TRN-03, TRN-09, TRN-10 |  | AIG-GOV-02, AIG-OPS-05, AIG-OPS-06, AIG-GOV-06, AIG-AIMS-01, AIG-AIMS-03 | ISO 5.1, 5.3, 7.1; A.2.2, A.3.2 | AIG-GOV-06 proposed governance; Playbook roles
ROL-02 | AI Assurance Board | Strategic oversight | Collective strategic oversight and higher-risk decision-making. | Provide assurance and endorsement on strategic direction and higher-risk cases; oversee risk, performance, exceptions and improvement; sponsor management review and assurance responses. | Proposed: Assurance and endorsement of high-risk cases, with approval remaining with the relevant delivery forum under delegation; Critical escalated to Executive Sponsor/Leadership, subject to approved Terms of Reference and delegations. | Receives Working Group recommendations and critical escalations; refers specialist matters to the relevant accountable function. |  |  | Proposed |  | Level 5 — AI Governance Leader | TRN-01, TRN-09, TRN-10 |  | AIG-DEC-03, AIG-OPS-05, AIG-OPS-06, AIG-GOV-06, AIG-AIMS-01, AIG-AIMS-03 | ISO 5.1, 5.3, 9.3; A.3.2 | AIG-GOV-06 Terms of Reference
ROL-03 | AI Governance Working Group | Operational governance | Cross-functional coordination, triage and medium-risk assurance. | Coordinate intake, AGPI, register and assessments; scrutinise evidence; assure and recommend on medium-risk cases; recommend high/critical decisions; track conditions and actions. | Proposed: Assurance and recommendation on medium-risk cases, with approval remaining with the relevant delivery forum under delegation; recommends High/Critical decisions. | Escalates High to the Board and Critical to Board/Executive Sponsor; involves control functions whenever their authority is engaged. |  |  | Proposed |  | Level 4 — AI Specialist | TRN-01, TRN-04, TRN-05, TRN-09, TRN-10 |  | AIG-INV-03, AIG-INV-04, AIG-ASS-01, AIG-ASS-02, AIG-ASS-03 and AIG-ASS-04, AIG-DEC-03, AIG-GOV-06, AIG-AIMS-03 | ISO 5.3, 8.1; A.3.2 | AIG-GOV-06 Terms of Reference
ROL-04 | AI Assurance Board Chair | Strategic and operational interface | Lead the Council’s AI direction and chair strategic governance. | Set direction; chair the Board; sponsor coherent prioritisation; ensure decisions and escalations reach the correct authority; promote capability and responsible innovation. | Chairing and recommendation authority only until delegations and Terms of Reference are formally approved. Chair to be confirmed by the Council (proposed: Executive Sponsor). | Works with Executive Sponsor and AI Governance Lead; escalates authority, resource and systemic-risk issues. |  |  | Proposed |  | Level 5 — AI Governance Leader | TRN-01, TRN-03, TRN-09, TRN-10 |  | AIG-GOV-02, AIG-OPS-05, AIG-OPS-06, AIG-GOV-06, AIG-AIMS-01 | ISO 5.1, 5.3, 7.4; A.3.2 | Playbook governance roles; AIG-GOV-06
ROL-05 | AI Governance Lead | AIMS management | Operate and continually improve the AIMS on behalf of accountable leadership. | Maintain scope, policy, SoA, registers, triage, governance workflow, metrics, evidence, training design, reporting, audits, management review and corrective actions. | Process administration and recommendation authority; no independent power to approve cases or accept risk outside confirmed delegation. | Escalates material risks, overdue actions, exceptions and evidence gaps to the relevant owner, Working Group, Board or Executive Sponsor. |  |  | Proposed |  | Level 5 — AI Governance Leader | TRN-01 to TRN-12 as applicable |  | AIG-GOV-01 to AIG-GOV-03, AIG-GOV-06, AIG-INV-01, AIG-INV-03, AIG-INV-04, AIG-ASS-01 to AIG-ASS-11, AIG-DEC-03, AIG-OPS-01, AIG-OPS-03, AIG-OPS-05, AIG-OPS-06, AIG-AIMS-01 to AIG-AIMS-04 | ISO 4.4, 5.3, 7.2-7.5, 9-10; A.3.2 | Playbook roles; AIG-GOV-06 and AIG-AIMS-03 IMP-05/IMP-09
ROL-06 | Governance Secretariat | Operational governance | Maintain reliable governance records and action tracking. | Schedule meetings; manage agendas, papers, conflicts, minutes, decisions, conditions, action logs and links to the AI Register and its Evidence index. | Administrative control only; cannot approve cases, close conditions or vary recorded decisions without authorised instruction. | Escalates missing papers, overdue actions, conflicts and decision-record inconsistencies to the Chair and AI Governance Lead. |  |  | Proposed |  | Level 2 — AI User / Practitioner | TRN-01, TRN-04, TRN-09 |  | AIG-INV-04, AIG-DEC-03, AIG-OPS-05, AIG-GOV-06 | ISO 7.5; A.3.2, A.6.2.3 | AIG-GOV-06 secretariat responsibilities
ROL-07 | Service Owner | Service accountability | Accountable owner for service outcomes and proportionate governance of an AI use. | Register the use; ensure assessments and controls; own risk and benefits; resource human oversight; approve operational procedures; monitor performance; report incidents and material change. | Proposed: Low-risk decision by the officer or forum with confirmed delegation (Service Owner/Service Manager only if delegated), recorded in AIG-DEC-03 or approved minutes; the AI Register records the reference. Cannot override specialist or higher-tier controls. | Escalates Medium/High/Critical cases and unresolved specialist findings; consults users and affected groups proportionately. |  |  | Proposed |  | Level 3 — AI Owner / Manager | TRN-01, TRN-03, TRN-04, TRN-05, TRN-10 |  | AIG-INV-03, AIG-INV-04, AIG-ASS-01, AIG-ASS-02, AIG-ASS-03, AIG-ASS-04, AIG-ASS-05, AIG-ASS-06 and AIG-ASS-07, AIG-DEC-03, AIG-OPS-03, AIG-OPS-01 | ISO 5.3, 8.1; A.5.4, A.9.2 | Playbook Service Owner; AIG-GOV-06 decision rights
ROL-08 | AI System Owner / Operational Lead | Operational delivery | Day-to-day accountability for safe, controlled system operation. | Maintain operating instructions, oversight, monitoring, access, logs, changes, thresholds, incidents, continuity and retirement evidence; keep the Service Owner informed. | Operational action within approved limits; may pause or invoke rollback where authorised by the deployment/incident plan. | Escalates threshold breaches, unapproved change, incidents, complaints and control failure to Service Owner and relevant specialists. |  |  | Proposed |  | Level 3 — AI Owner / Manager | TRN-01, TRN-02, TRN-04, TRN-10, TRN-11 |  | AIG-INV-04, AIG-ASS-09, AIG-OPS-03, AIG-ASS-11, AIG-OPS-01 | ISO 8.1, 9.1; A.6.2.6-A.6.2.8, A.9.2 | Playbook lifecycle; AIG-OPS-01 rollout roles
ROL-09 | Product / Technical Delivery Lead | Technical delivery | Ensure technical design, testing, release and change evidence meets approved requirements. | Document system design; perform verification/validation; manage environments and release; implement monitoring, security and rollback controls; disclose limitations and dependencies. | Technical recommendation and release execution within approved change and deployment authority; no governance risk acceptance. | Escalates failed tests, limitations, security issues, drift and material change to System/Service Owner and governance functions. |  |  | Proposed |  | Level 4 — AI Specialist | TRN-01, TRN-02, TRN-05, TRN-07, TRN-11 |  | AIG-ASS-02, AIG-ASS-09, AIG-ASS-11, AIG-OPS-01 | ISO 8.1; A.6.2.2-A.6.2.8, A.7.2-A.7.6 | AIG-OPS-01 technical/delivery role; Model Card
ROL-10 | Data Owner / Data Governance | Specialist control | Authorise and assure appropriate data use, quality and stewardship. | Confirm data ownership, provenance, lawful/approved access, quality, representativeness, lineage, retention and monitoring; resolve data-control exceptions. | Retains data-governance authority under Council policy; can withhold data approval where requirements are unmet. | Escalates material data risks to Service Owner, DPO/IG, SIRO and governance bodies as appropriate. |  |  | Proposed |  | Level 4 — AI Specialist | TRN-01, TRN-05, TRN-06, TRN-11 |  | AIG-ASS-02, AIG-ASS-04, AIG-ASS-05, AIG-ASS-09 | ISO 5.3, 8.1; A.4.3, A.7.2-A.7.6 | Playbook data roles and lifecycle controls
ROL-11 | DPO / Information Governance | Specialist control | Provide independent data-protection and information-governance advice and assurance. | Determine DPIA needs; advise on lawful basis, transparency, rights, minimisation, retention, sharing and high-risk processing; maintain statutory escalation where applicable. | Retains statutory/professional authority; governance bodies cannot waive legal data-protection requirements. | Escalates unresolved high privacy risk through statutory and Council routes; consults Legal, SIRO, Security and affected services. |  |  | Proposed |  | Level 4 — AI Specialist | TRN-01, TRN-05, TRN-06, TRN-10 |  | AIG-ASS-04, AIG-ASS-05, AIG-ASS-08, AIG-OPS-03, AIG-GOV-06 | ISO 5.3, 7.4; A.5.2-A.5.5, A.7 | Playbook DPO role; AIG-GOV-06 retained authority
ROL-12 | SIRO / Information Risk | Strategic specialist control | Oversee material information risk and assurance. | Advise on information risk appetite, ownership, escalation and assurance; sponsor resolution of systemic or critical information risks. | Retains information-risk authority under Council governance and approved risk delegations. | Escalates material information risks to Executive Leadership and appropriate governance bodies. |  |  | Proposed |  | Level 5 — AI Governance Leader | TRN-01, TRN-07, TRN-09, TRN-10 |  | AIG-ASS-11, AIG-GOV-06, AIG-AIMS-01, AIG-AIMS-03 | ISO 5.1, 5.3, 6.1; A.3.2 | Playbook SIRO role; AIG-GOV-06 membership
ROL-13 | Cyber Security | Specialist control | Assess and control AI security, misuse, resilience and supplier-security risks. | Perform threat/risk review; define access, logging, testing and vulnerability requirements; review incidents and supplier evidence; set security closure criteria. | Retains security authority under Council policy; can require remediation or escalation before release. | Escalates critical vulnerabilities, misuse and incidents through Council security and governance routes. |  |  | Proposed |  | Level 4 — AI Specialist | TRN-01, TRN-07, TRN-10, TRN-11 |  | AIG-ASS-08, AIG-OPS-03, AIG-ASS-11, AIG-OPS-01 | ISO 8.1; A.4.4-A.4.5, A.6.2.4-A.6.2.8 | Playbook Security role; AIG-ASS-11
ROL-14 | Legal Services / Monitoring Officer | Specialist control | Advise on applicable law, powers, contracts, delegations and legal risk. | Maintain legal input to requirements, decisions, transparency, equality/human rights, procurement and incidents; confirm lawful authority and governance route. | Retains professional/statutory authority; legal requirements and Council delegations cannot be displaced by AIMS governance. | Escalates unresolved legality, authority or public-law concerns to the correct statutory and leadership route. |  |  | Proposed |  | Level 4 — AI Specialist | TRN-01, TRN-05, TRN-08, TRN-09, TRN-10 |  | AIG-ASS-04 to AIG-ASS-08, AIG-DEC-03, AIG-GOV-06, AIG-AIMS-01 | ISO 4.2, 5.3, 7.4; A.2.3, A.5 | Playbook Legal role; AIG-GOV-06 retained authority
ROL-15 | Procurement / Commercial / Contract Owner | Specialist control | Control AI procurement and ongoing supplier obligations. | Trigger governance early; perform due diligence; embed mandatory clauses; manage evidence rights, change, performance, incidents, renewal and exit. | Retains procurement/commercial authority; cannot accept material AI risk outside approved delegations. | Escalates supplier gaps, exceptions, unnotified change and exit/resilience risks to Service Owner, Legal, Security and governance bodies. |  |  | Proposed |  | Level 3 — AI Owner / Manager | TRN-01, TRN-05, TRN-08, TRN-10 |  | AIG-INV-03, AIG-ASS-08, AIG-ASS-11, AIG-OPS-01 | ISO 8.1; A.10.2-A.10.4 | Playbook Procurement role; Supplier Questionnaire
ROL-16 | Equality / Human Rights / Safeguarding Leads | Specialist control | Assure impacts on protected, vulnerable and affected people. | Determine assessment/engagement needs; challenge impact analysis and mitigations; advise on accessibility, safeguarding and monitoring; review adverse outcomes. | Retains specialist authority under relevant Council policies and statutory duties. | Escalates material or unresolved harm to Service Owner, Legal, governance bodies and safeguarding routes. |  |  | Proposed |  | Level 4 — AI Specialist | TRN-01, TRN-05, TRN-10 |  | AIG-ASS-04, AIG-ASS-06, AIG-ASS-07, AIG-OPS-05, AIG-OPS-03 | ISO 4.2, 6.1; A.5.2-A.5.5, A.8.2-A.8.5 | Responsible AI, Equality and Human Rights templates
ROL-17 | Communications / Engagement / Complaints | Operational and specialist interface | Provide accessible communication, participation, feedback and redress routes. | Plan internal/external communications; support affected-group engagement; ensure accessible service information; route complaints and track themes and responses. | Communication approval remains with authorised service/corporate owners; complaints retain existing Council authority and independence. | Escalates material complaint trends, misinformation, public-interest issues and accessibility failures. |  |  | Proposed |  | Level 3 — AI Owner / Manager | TRN-01, TRN-02, TRN-05, TRN-10 |  | AIG-ASS-07, AIG-ASS-10, AIG-OPS-05, AIG-OPS-03, AIG-OPS-01 | ISO 7.3-7.4; A.3.3, A.8.2-A.8.5 | AIG-OPS-01 communications role; Playbook awareness
ROL-18 | Internal Audit / Independent Assurance | Independent assurance | Provide independent, risk-based assurance over AIMS design and operation. | Approve audit scope/programme; assess control design, implementation and effectiveness; report findings independently; follow up agreed actions. | Independent assurance authority under the Council audit framework; does not own or operate audited controls. | Reports findings to appropriate audit and governance bodies; escalates overdue or unacceptable management responses. |  |  | Proposed |  | Level 4 — AI Specialist | TRN-01, TRN-09, TRN-12 |  | AIG-OPS-05, AIG-OPS-06, AIG-GOV-06, AIG-AIMS-01 to AIG-AIMS-04 | ISO 9.2; A.3.2 | Playbook Internal Audit role; AIG-AIMS-03 IMP-14
ROL-19 | All employees / AI users | Council-wide | Use AI only within approved policy, training and system instructions. | Complete required learning; register or disclose AI use; protect information; follow human-oversight and acceptable-use rules; report concerns, errors and incidents promptly. | No authority to introduce or materially change Council AI unless assigned through an approved role and process. | Raise concerns through line management, Service Owner, AI governance, security, data-protection, whistleblowing or complaints routes as applicable. |  |  | Proposed |  | Level 1 — AI Awareness | TRN-01; TRN-02 for AI users |  | AIG-GOV-02, AIG-INV-01, AIG-INV-03, AIG-OPS-03 | ISO 7.2-7.3; A.3.3, A.4.6, A.9.2 | Playbook All Employees role and competency policy
ROL-20 | Data Steward | Service accountability | Look after the quality, meaning and day-to-day use of the data an AI system relies on, on behalf of the Data Owner. | Maintain data definitions and quality checks; keep data lineage and provenance records current; check that data used by AI matches the approved purpose; keep the Information Asset Register entry and the AI Register Information asset reference (AIG-INV-04 column AA) aligned; raise data quality or misuse issues. | No authority to approve AI use or new uses of data; recommends to the Data Owner and Service Owner. | Escalate to the Data Owner, Service Owner, DPO or Information Governance as applicable. |  |  | Proposed |  | Level 3 — AI Owner / Manager | TRN-01, TRN-03, TRN-04, TRN-05, TRN-10 |  | AIG-GOV-02 §5.6 and Appendix A.2; AIG-INV-04 column AA; AIG-ASS-05; AIG-ASS-09 | ISO 5.3, 7.2; A.7.4, A.7.5 | Proposed v3.9.10 data governance role (Proposed — for Council confirmation)

## Competence Matrix
The Council — AIMS Competence Matrix and Assessment Record
AIG-AIMS-04 · v1.3 draft · Draft for Council review · OFFICIAL · ISO/IEC 42001:2023
Purpose: define required role-group competence across the Playbook domains and control assessment, gaps, remedial action and evidence.
Current position: proficiency numbers are required levels, not current scores. Every group is marked Not assessed until named people are assessed using approved methods and evidence; training attendance alone is insufficient.
Group ID | Role group | Playbook competency level | AI literacy | Governance / accountability | Risk | Responsible AI | Data / IG | Security / resilience | Operational application | Leadership / oversight | Evidence / assessment method | Assessment frequency | Current assessment status | Current result | Gap / remedial action | Owner | Due date | Evidence location | Related objectives / risks / learning | Record QA
CMP-01 | All employees | Level 1 — AI Awareness | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Completion plus short knowledge check | At induction; refresh at least annually | Not assessed |  | Assess the target population and completion baseline once the programme is approved. | HR / L&D with AI Governance Lead |  |  | OBJ-08; R-05; IMP-09; TRN-01
CMP-02 | Regular AI users / practitioners | Level 2 — AI User / Practitioner | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 1 | Scenario-based knowledge check and supervisor observation | Before approved use; annual refresh and on material change | Not assessed |  | Identify the user population and validate practice against approved instructions. | Service Owner / Line Manager |  |  | OBJ-04, OBJ-05; R-05; TRN-01, TRN-02
CMP-03 | Managers of AI-using staff | Level 3 — AI Owner / Manager | 2 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | Manager module, scenario exercise and management review | On appointment; annual refresh | Not assessed |  | Confirm which managers supervise AI use and assess governance decision capability. | Directorate Leadership / HR-L&D |  |  | OBJ-08; R-04, R-05; TRN-03
CMP-04 | Service Owners | Level 3 — AI Owner / Manager | 3 | 4 | 4 | 4 | 3 | 3 | 4 | 4 | Case-based assessment using a real governance submission | Before approval authority; annual and after control failure | Not assessed |  | Assess named Service Owners after appointment; remediate any lifecycle or accountability gap. | AI Governance Lead / Directorate Leadership |  |  | OBJ-02 to OBJ-08; R-04, R-05; IMP-05, IMP-09
CMP-05 | AI System Owners / Operational Leads | Level 3 — AI Owner / Manager | 3 | 3 | 4 | 3 | 3 | 4 | 4 | 3 | Operational simulation, threshold/rollback exercise and record review | Before go-live; at least annually and on material change | Not assessed |  | Validate monitoring, escalation, incident and change-control competence for each live system. | Service Owner / AI Governance Lead |  |  | OBJ-04, OBJ-07; R-05, R-11, R-12; TRN-04, TRN-10, TRN-11
CMP-06 | Product / Technical / Data Science specialists | Level 4 — AI Specialist | 4 | 3 | 4 | 4 | 3 | 4 | 4 | 2 | Technical portfolio, test evidence, peer review and scenario exercise | Before technical authority; annual CPD review | Not assessed |  | Map required disciplines to each system and confirm specialist depth, peer review and succession. | Technical Leadership / Service Owner |  |  | OBJ-04; R-05, R-07, R-10, R-11; TRN-07, TRN-11
CMP-07 | Data, privacy and information-governance specialists | Level 4 — AI Specialist | 3 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | Professional evidence, case review and challenge exercise | On assignment; annual CPD review | Not assessed |  | Validate AI-specific application of professional expertise and access to external advice. | Relevant Function Head |  |  | OBJ-03, OBJ-04; R-05, R-07; TRN-05, TRN-06
CMP-08 | Cyber Security specialists | Level 4 — AI Specialist | 3 | 3 | 4 | 3 | 3 | 4 | 3 | 3 | Threat-model review, technical exercise and professional evidence | On assignment; annual CPD review and threat change | Not assessed |  | Validate AI-specific threat, misuse, resilience and supplier-security competence. | Head of Cyber Security |  |  | OBJ-04, OBJ-07; R-05, R-10, R-12; TRN-07, TRN-10, TRN-11
CMP-09 | Legal, equality, human-rights and safeguarding specialists | Level 4 — AI Specialist | 3 | 4 | 4 | 4 | 3 | 2 | 3 | 3 | Professional evidence and cross-functional case challenge | On assignment; annual CPD review and legal change | Not assessed |  | Validate AI-specific public-law, equality, rights and safeguarding capability. | Relevant Function Head |  |  | OBJ-03, OBJ-05; R-05, R-06, R-08, R-13; TRN-05
CMP-10 | Procurement, commercial and contract owners | Level 3 — AI Owner / Manager | 3 | 3 | 4 | 3 | 3 | 3 | 4 | 3 | Supplier case assessment and contract-control review | Before material AI procurement; annual refresh | Not assessed |  | Validate early governance triggering, due diligence, clauses, evidence rights and exit competence. | Head of Procurement / AI Governance Lead |  |  | OBJ-06; R-05, R-09, R-15; TRN-08
CMP-11 | Governance Secretariat and Working Group members | Level 4 — AI Specialist | 3 | 4 | 4 | 4 | 3 | 3 | 4 | 3 | Induction, calibrated case exercise and decision-record sample | Before participation; annual calibration | Not assessed |  | Assess consistent triage, evidence challenge, conflicts, decisions and escalation. | AI Governance Lead / Working Group Chair |  |  | OBJ-02, OBJ-08; R-03 to R-05; TRN-04, TRN-09
CMP-12 | AI Assurance Board and Executive Sponsor | Level 5 — AI Governance Leader | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | Board induction, strategic scenario and management-review evaluation | Before decision authority; annual update | Not assessed |  | Confirm leadership understanding of accountability, risk acceptance, resources and management review. | AI Governance Lead |  |  | OBJ-08; R-01, R-04, R-05; TRN-09, TRN-10
CMP-13 | AI Governance Lead and Internal Audit | Level 5 / Level 4 specialist | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Advanced AIMS assessment, audit/implementation evidence and independent review | On appointment; annual CPD and external-change review | Not assessed |  | Confirm sufficient ISO/IEC 42001, audit, regulatory and practical governance capability; obtain expert support for gaps. | Executive Sponsor / Head of Internal Audit |  |  | OBJ-08; R-05, R-14; IMP-05, IMP-09, IMP-14; TRN-12

## Learning Plan
The Council — AIMS Learning and Awareness Plan
AIG-AIMS-04 · v1.3 draft · Draft for Council review · OFFICIAL · ISO/IEC 42001:2023
Purpose: define role-based learning, timing, outcomes, delivery, completion, assessment and effectiveness evidence required to support competent AIMS operation.
Current position: modules and targets are proposed designs. No delivery, completion or effectiveness is claimed; approve audience, content, accessibility, dates, pass criteria, ownership and evidence before launch.
Module ID | Module | Audience | Competency level | Requirement | Trigger / deadline | Learning outcomes | Delivery method | Owner | Status | Planned date | Recurrence | Assessment / effectiveness | Completion target | Completion rate | Evidence location | Review date | Related objectives / risks / actions | ISO / SoA links | Decision / design note | Record QA
TRN-01 | AI Awareness | All employees, agency workers and relevant contractors | Level 1 | Mandatory | At induction and before Council AI use | Recognise AI; understand Council principles, registration, acceptable use, data handling, human accountability and concern routes. | Accessible e-learning with short knowledge check | HR / L&D with AI Governance Lead | Draft design |  | At least annually | Completion, pass score, feedback and incident trend | 100% | 0% |  |  | OBJ-08; R-05; IMP-09 | ISO 7.2-7.3; A.3.3, A.4.6 | Confirm target population, pass score, accessibility and LMS reporting.
TRN-02 | Approved AI Use, Acceptable Use and Data Handling | Regular AI users and practitioners | Level 2 | Mandatory for AI users | Before access to an approved AI system | Apply approved instructions; protect information; verify outputs; maintain human responsibility; report errors, incidents and suspected unregistered use. | System-linked e-learning plus local briefing | Service Owner / Information Governance | Draft design |  | Annual and on instruction change | Knowledge check, observed practice, user error and incident data | 100% | 0% |  |  | OBJ-04, OBJ-05; R-05, R-10; CMP-02 | ISO 7.2-7.3, 8.1; A.4.6, A.9.2 | Link access provisioning to completion where technically and lawfully appropriate.
TRN-03 | AI Governance for Managers | Managers of staff who use, commission or oversee AI | Level 3 | Mandatory for in-scope managers | On appointment or before supervisory responsibility | Recognise governance triggers; assign owners; prevent shadow AI; support oversight, challenge, escalation and staff capability. | Workshop or facilitated e-learning with scenarios | AI Governance Lead / HR-L&D | Draft design |  | At least annually | Scenario score, manager confidence, registration and escalation trends | 100% | 0% |  |  | OBJ-01, OBJ-08; R-02, R-05; CMP-03 | ISO 5.3, 7.2-7.3; A.4.6, A.9.2 | Confirm manager population and appointment timeframe.
TRN-04 | Service and System Owner Lifecycle Governance | Service Owners, System Owners, operational leads and secretariat | Level 3 | Mandatory for assigned owners | Before ownership or approval authority | Operate intake, AGPI, assessments, decision records, conditions, monitoring, material change, evidence, incidents and retirement. | Facilitated case-based workshop using suite artefacts | AI Governance Lead | Draft design |  | Annual calibration and on process change | Completed case, evidence-quality review and governance rework rate | 100% | 0% |  |  | OBJ-01, OBJ-02, OBJ-04; R-03 to R-05; IMP-05, IMP-09 | ISO 5.3, 7.2, 8.1; A.3.2, A.6.2, A.9.2 | Use representative Council cases and record assessor conclusions.
TRN-05 | Responsible AI and Impact Assessment | Owners, governance members, legal/equality/rights/safeguarding and engagement roles | Levels 3-4 | Mandatory where role applies | Before assessing or approving potentially material impacts | Identify people and societal impacts; apply Responsible AI, DPIA, equality and human-rights assessments; plan participation, mitigation and monitoring. | Cross-functional workshop and case challenge | AI Governance Lead with specialist functions | Draft design |  | Annual and on material legal/process change | Assessment sample quality, challenge outcomes, action closure and complaints | 100% | 0% |  |  | OBJ-03, OBJ-05; R-06, R-08, R-13; CMP-04, CMP-07, CMP-09 | ISO 4.2, 6.1, 8.1; A.5.2-A.5.5, A.8.2-A.8.5 | Specialist functions define required depth and sign-off.
TRN-06 | Data Protection, Information Governance and Data Quality | Owners, practitioners, data and IG roles | Levels 2-4 | Mandatory / role-based | Before relevant data processing or approval | Apply lawful/approved data use, minimisation, transparency, rights, provenance, quality, representativeness, retention and sharing controls. | Role-based modules plus case clinics | DPO / Information Governance / Data Governance | Draft design |  | Annual and on material change | Assessment quality, data exceptions, DPIA outcomes and audit findings | 100% | 0% |  |  | OBJ-03, OBJ-04; R-07, R-13; CMP-02, CMP-07 | ISO 7.2, 8.1; A.4.3, A.5, A.7 | Integrate with existing mandatory information-governance learning.
TRN-07 | AI Security, Misuse and Resilience | Technical, security, owner and incident roles | Levels 3-4 | Mandatory for relevant roles | Before design approval, security review or operational ownership | Address AI-specific threats, access, logging, misuse, vulnerabilities, supplier controls, resilience, monitoring and secure rollback. | Technical workshop, threat modelling and tabletop exercise | Cyber Security | Draft design |  | Annual and on threat/material system change | Threat-model quality, exercise outcomes, findings and incident trends | 100% | 0% |  |  | OBJ-04, OBJ-07; R-10, R-12; CMP-05, CMP-06, CMP-08 | ISO 7.2, 8.1; A.4.4-A.4.5, A.6.2.4-A.6.2.8 | Align to corporate security training and incident processes.
TRN-08 | AI Procurement, Supplier Assurance and Contract Controls | Procurement, commercial, Legal, Service Owners and contract managers | Levels 3-4 | Mandatory for material AI sourcing | Before market engagement, contract, renewal or material change | Trigger governance early; conduct due diligence; specify evidence, change, incident, performance, audit, continuity and exit obligations. | Procurement clinic and supplier-case assessment | Procurement / Legal / AI Governance Lead | Draft design |  | Annual and on template/legal change | Supplier case quality, clause exceptions, findings, change notices and exit readiness | 100% | 0% |  |  | OBJ-06; R-09, R-10, R-15; CMP-10 | ISO 7.2, 8.1; A.10.2-A.10.4 | Embed triggers into procurement guidance and assurance gates.
TRN-09 | Governance Decision-Maker Induction and Calibration | Executive Sponsor, Board, Working Group, chairs and secretariat | Levels 4-5 | Mandatory before governance participation | Before first meeting or decision | Understand mandate, delegations, conflicts, evidence expectations, risk tiering, specialist authority, decision recording, escalation and management review. | Induction pack, facilitated case calibration and annual update | AI Governance Lead | Draft design |  | Annual and on Terms of Reference/delegation change | Attendance, calibration consistency, decision-record quality and rework | 100% | 0% |  |  | OBJ-02, OBJ-08; R-01, R-03 to R-05; IMP-05 | ISO 5.1, 5.3, 7.2-7.4, 9.3; A.3.2 | Do not grant decision authority solely through training; formal appointment is also required.
TRN-10 | AI Incident, Concern, Complaint and Tabletop Response | Owners, governance, security, DPO, Legal, communications and complaints roles | Levels 2-5 | Mandatory where role applies | Before go-live or incident-response duty | Triage and contain; notify; preserve evidence; communicate; investigate root cause; manage complaints/redress; verify corrective-action effectiveness. | Cross-functional tabletop using AIG-OPS-03 | Incident Lead / AI Governance Lead | Draft design |  | At least annually and after material incident | Exercise results, response time, missed hand-offs, action closure and recurrence | 100% | 0% |  |  | OBJ-05, OBJ-07; R-08, R-12; IMP-13 | ISO 7.2-7.4, 10.2; A.3.3, A.8.3-A.8.4 | Align severity and notification with Council incident frameworks.
TRN-11 | Technical Verification, Validation, Monitoring and Change | Technical leads, data scientists, System Owners and reviewers | Level 4 | Mandatory for technical authority | Before testing, release, monitoring or material-change decisions | Define acceptance criteria; test limitations and affected groups; monitor drift/performance; maintain traceability; trigger change control and rollback. | Technical lab, peer review and evidence assessment | Technical Leadership / AI Governance Lead | Draft design |  | Annual CPD and on material technology change | Test/evidence sample quality, threshold breaches, change and incident trends | 100% | 0% |  |  | OBJ-04; R-07, R-10, R-11; CMP-05, CMP-06 | ISO 7.2, 8.1, 9.1; A.6.2.5-A.6.2.8, A.7 | Tailor depth to system risk and technical role.
TRN-12 | Advanced AIMS Implementation and Independent Assurance | AI Governance Lead, nominated deputies and Internal Audit | Levels 4-5 | Mandatory for AIMS/audit leads | Before leading implementation or independent audit | Apply ISO/IEC 42001 requirements; maintain scope, SoA, objectives, risks and evidence; plan audits and management review; manage nonconformity and improvement. | Advanced practitioner course, supervised application and independent review | Executive Sponsor / Head of Internal Audit | Draft design |  | Annual CPD and standards change | Practical work product, audit quality, finding consistency and improvement outcomes | 100% | 0% |  |  | OBJ-08; R-05, R-14; IMP-02, IMP-14, IMP-15 | ISO clauses 4-10; Annex A | Confirm independence and avoid self-audit of controls operated by the same individual.

## Communications Plan
The Council — AIMS Communications Plan
AIG-AIMS-04 · v1.3 draft · Draft for Council review · OFFICIAL · ISO/IEC 42001:2023
Purpose: control AIMS messages, audiences, ownership, channels, triggers, accessibility, evidence and effectiveness for internal and external interested parties.
Current position: all activities are draft designs. Approve the message, sender, audience, timing, accessibility, confidentiality and evidence before issue; retain actual publication and effectiveness records.
Communication ID | Objective / core message | Audience / interested party | Owner | Sender / approver | Channel | Timing / trigger | Frequency | Accessibility / consultation | Required record / evidence | Status | Target date | Last issued | Effectiveness measure | Related objectives / risks / actions | ISO / SoA links | Decision / design note | Record QA
COM-01 | Formal leadership adoption: explain scope, mandate, accountable ownership, delegations, resources and effective date. | Executive Leadership, governance bodies, control-function heads and directorate leadership | Executive Sponsor | Adopting authority / corporate communications | Formal decision, leadership briefing and controlled publication | On approval of the AIMS and any material governance change | Once, then on material change | Accessible summary; opportunity for questions and recorded specialist consultation | Approval record, published message, audience list, questions/actions | Draft design |  |  | Receipt, leadership understanding, unresolved questions and assigned actions | OBJ-08; R-01, R-04; IMP-01, IMP-03, IMP-05 | ISO 5.1-5.3, 7.3-7.4; A.2.2, A.3.2 | Must not describe draft documents as approved or operational.
COM-02 | All-staff awareness: approved AI use, registration, acceptable-use rules, human responsibility and routes for concerns. | All employees, agency workers and relevant contractors | AI Governance Lead / HR-L&D | Executive Sponsor / Internal Communications | Intranet, staff bulletin, learning campaign and manager cascade | At launch; induction; major policy or risk change | Annual campaign plus triggered updates | Accessible formats, plain language and feedback route | Published content, audience/reach data, learning link and FAQs | Draft design |  |  | Reach, learning completion, knowledge score, registrations and reported shadow AI | OBJ-01, OBJ-08; R-02, R-05; IMP-06, IMP-09 | ISO 7.3-7.4; A.3.3, A.4.6, A.9.2 | Align with AIG-INV-01 staff guide and approved policy.
COM-03 | Manager and owner briefing: governance triggers, accountability, approval tiers, evidence and escalation. | Managers, Service Owners, System Owners and delivery leads | AI Governance Lead | AI Governance Lead / Directorate Leadership | Briefing session, manager toolkit and office hours | Before ownership or supervisory duty; at launch | At least annually and on process change | Scenario-led, role-specific and available in accessible formats | Attendance, toolkit version, questions, actions and competence assessment | Draft design |  |  | Attendance, scenario results, registration timeliness and governance rework | OBJ-02, OBJ-08; R-03 to R-05; IMP-05, IMP-09 | ISO 5.3, 7.2-7.4; A.3.2, A.4.6 | Coordinate with TRN-03 and TRN-04.
COM-04 | AI Register and intake guidance: when and how to register, expected response, status meanings and support route. | Council staff, project teams, procurement, suppliers working through Council teams | AI Governance Lead | AI Governance Working Group Chair | Intranet guidance, intake form, drop-in clinics and project templates | At launch; new project/procurement; form/process change | Continuous availability; quarterly reminder during implementation | Accessible form and guidance; assisted route for users who need it | Published version, usage data, enquiries, response times and form changes | Draft design |  |  | Registration volume/completeness, abandoned requests, response time and user feedback | OBJ-01, OBJ-02; R-02, R-03; IMP-06, IMP-07 | ISO 7.4, 8.1; A.4.2, A.8.5, A.9.2 | Use one AI Register ID across all evidence.
COM-05 | Governance body induction and decision protocol: mandate, evidence, conflicts, specialist authority and decision records. | Executive Sponsor, Board, Working Group, secretariat and regular advisers | AI Governance Lead | AI Governance Lead / relevant Chair | Induction pack, calibrated case workshop and meeting standing items | Before participation and on appointment/delegation change | Annual calibration plus triggered update | Materials issued early; conflicts and accessibility needs captured | Attendance, declarations, calibration result, minutes and updated pack | Draft design |  |  | Decision consistency, evidence quality, conflicts handled and rework | OBJ-02, OBJ-08; R-01, R-03, R-04; IMP-05 | ISO 5.3, 7.2-7.4; A.3.2 | Training does not itself confer decision authority.
COM-06 | Specialist-control integration: confirm retained authority, hand-offs, service levels, evidence and escalation. | DPO/IG, SIRO, Security, Legal, Procurement, Data, Equality, Human Rights, Safeguarding, Audit | AI Governance Lead | Executive Sponsor / relevant Function Heads | Cross-functional workshop, operating agreement and process maps | Before AIMS activation and on material organisational change | At least annually | Allow specialist functions to document constraints and resourcing needs | Agreed interfaces, action log, service expectations and escalation records | Draft design |  |  | Hand-off failures, overdue reviews, disputed authority and resource actions | OBJ-02, OBJ-08; R-04, R-05; IMP-05 | ISO 5.3, 7.1, 7.4; A.3.2 | AIG-GOV-06 states specialist functions retain their authority.
COM-07 | Supplier and market communication: disclose Council AI governance, due-diligence evidence, contract, change, incident and exit expectations. | Bidders, suppliers, partners, contract owners and procurement teams | Procurement / Contract Owner | Legal / authorised procurement approver | Procurement documents, contracts, supplier briefings and review meetings | Before market engagement; contract/renewal; material supplier change | Per procurement and scheduled supplier review | Proportionate to market and procurement law; accessible supplier route for clarification | Issued requirements, questions, due diligence, clauses, exceptions and review minutes | Draft design |  |  | Compliance, exceptions, evidence timeliness, unnotified change and exit readiness | OBJ-06; R-09, R-10, R-15; IMP-10 | ISO 7.4, 8.1; A.10.2-A.10.4 | Do not disclose sensitive security detail outside approved channels.
COM-08 | Live-system operational communication: approved purpose, limits, instructions, oversight, thresholds, escalation and rollback. | Authorised users, supervisors, support teams and operational owners | AI System Owner / Service Owner | Service Owner and relevant control owners | Operating procedure, user briefing, in-product guidance and release notice | Before go-live/access; material change; threshold or incident response | At every release/change plus periodic refresh | Role-specific, accessible and tested with representative users | Approved instructions, attendance/acknowledgement, release record and user feedback | Draft design |  |  | Instruction comprehension, user error, overrides, incidents and support demand | OBJ-04, OBJ-05, OBJ-07; R-08, R-10, R-11 | ISO 7.3-7.4, 8.1; A.6.2.6-A.6.2.8, A.9.2 | Link to AIG-ASS-09 Model Card and AIG-OPS-01 rollout evidence.
COM-09 | Resident/service-user transparency: explain relevant AI use, purpose, human role, significant limits, data/rights, accessibility, contact and redress. | Residents, service users, communities and affected groups | Service Owner / Communications | Authorised service owner with DPO/Legal/specialist review | Service pages, notices, letters, assisted channels and engagement sessions | Before applicable use; material purpose/impact change; emerging concern | Continuous availability and periodic review | Plain language, accessible formats, language/assisted routes and proportionate affected-group testing | Approved content, accessibility/user testing, consultation, publication and change records | Draft design |  |  | Understanding, accessibility findings, contact/complaint themes and resulting service changes | OBJ-03, OBJ-05; R-06, R-08, R-13 | ISO 4.2, 7.4; A.5.4, A.8.2-A.8.5 | Apply proportionality; legal/privacy notices remain subject to specialist approval.
COM-10 | Urgent incident and risk communication: what happened, containment, affected parties, actions, contact and update cadence. | Incident team, leadership, regulators/partners where required, staff, residents and media as applicable | Incident Lead | Authorised incident/corporate communications owner with specialist clearance | Secure incident channels, notifications, service updates and holding statements | Severity-based trigger under approved incident plan | As required until closure | Protect confidentiality; use accessible/public channels where affected people need timely information | Incident log, approvals, notifications, message versions, receipt and follow-up | Draft design |  |  | Notification timeliness, accuracy, reach, misinformation, complaints and lessons learned | OBJ-05, OBJ-07; R-08, R-12; IMP-13 | ISO 7.4, 10.2; A.3.3, A.8.3-A.8.4 | Align severity, notification and legal duties with corporate processes.
COM-11 | AIMS performance and assurance reporting: objectives, risk, inventory, control effectiveness, incidents, learning, audit and actions. | Working Group, Board, Executive Sponsor, leadership and assurance committees | AI Governance Lead | Relevant Chair / Executive Sponsor | Dashboard, governance report, management-review pack and audit updates | Approved reporting calendar; material exception; management review | Monthly during implementation; at least quarterly thereafter | Clear definitions, data-quality notes, exceptions and decision requests | Controlled report, source data, minutes, decisions and action log | Draft design |  |  | Data completeness/accuracy, decisions made, overdue actions and trend response | OBJ-01 to OBJ-08; R-14; IMP-12, IMP-14, IMP-15 | ISO 9.1-9.3, 10.1; A.8.5 | Do not imply control effectiveness without operating evidence.
COM-12 | Learning, lessons and community of practice: share safe patterns, recurring issues, controls and improvement opportunities. | Owners, practitioners, specialists, governance members and interested staff | AI Governance Lead | AI Governance Lead / relevant specialist owner | Community sessions, clinics, anonymised case notes and learning bulletins | After pilots, incidents, complaints, audits and material reviews | Quarterly during implementation | Anonymise sensitive cases; ensure inclusive participation and accessible materials | Session records, anonymised learning, actions, feedback and control changes | Draft design |  |  | Participation, repeat issues, adopted improvements and competence feedback | OBJ-07, OBJ-08; R-05, R-12, R-14; IMP-07, IMP-13 | ISO 7.3-7.4, 10.1-10.2; A.4.6 | Share only approved and appropriately de-identified material.
COM-13 | Applicable-requirement and material-change updates: explain what changed, affected roles/systems, actions and effective date. | Leadership, governance, Service/System Owners and relevant control functions/suppliers | Legal Services / AI Governance Lead | Applicable requirement owner / authorised governance body | Targeted alert, change note, updated controlled documents and briefing | New/changed law, regulation, policy, standard, contract or risk context | Event-driven; periodic horizon review | Target only affected groups while maintaining an accessible authoritative record | Source assessment, applicability decision, affected records, communications and action closure | Draft design |  |  | Timeliness, affected-system coverage, action closure and outdated-document findings | OBJ-03, OBJ-08; R-13; IMP-04 | ISO 4.2, 6.1, 7.4, 9.1; A.2.3 | Coordinate with the AIMS applicable-requirements and change register (AIG-AIMS-05).

## Lists & Guidance
AIG-AIMS-04 — Definitions, Evidence Rules and Controlled-Use Guidance
Role status | Meaning |  | Assessment status | Meaning | Learning / communication status | Meaning
Proposed | Role design only; no person or body is appointed by this workbook. |  | Not assessed | Required profile is defined but current competence has not been assessed. | Draft design | Content/activity is proposed; nothing has been approved or issued.
Confirmed | Named appointee, authority/appointment evidence, deputy arrangements and review date are retained. |  | Assessment planned | Assessor, method, scope and date are agreed. | Approved | Authorised design, owner, audience, timing and evidence requirements are confirmed.
Vacant | Approved role has no current appointee; risk, interim cover and escalation should be recorded. |  | Assessed - competent | Evidence supports competence for the assigned role and scope, with review date. | Scheduled | Delivery/issue date and resources are confirmed.
Interim | Time-limited appointment with explicit authority, deputy/cover and review date. |  | Assessed - gap | A defined competence gap needs supervision, restriction, training or other remedial action. | Active | Recurring activity is operating and being monitored.
Suspended | Authority is temporarily suspended through an authorised decision. |  | Expired / reassess | Evidence is no longer current because of time, role, technology, control failure or material change. | Issued | A communication was issued and evidence retained.
Retired | Role is no longer required or is superseded through an approved change. |  |  |  | Complete | Planned delivery is finished and effectiveness evidence reviewed.
[5 empty] | Paused | Activity is formally paused with reason and review decision.
[5 empty] | Retired | Activity is superseded or no longer required through approved change.
Playbook competency levels
Level 1 | AI Awareness | All employees | Recognise AI, core principles, acceptable use and reporting routes.
Level 2 | AI User / Practitioner | People using AI in work | Use approved systems safely, verify outputs, protect information and follow instructions.
Level 3 | AI Owner / Manager | Managers and accountable owners | Own lifecycle governance, risk, human oversight, evidence and operational performance.
Level 4 | AI Specialist | Technical, legal, data, security and governance specialists | Apply specialist expertise to AI design, review, assurance and challenge.
Level 5 | AI Governance Leader | Executive and AIMS leaders | Set direction, exercise accountability, allocate resources, accept/escalate risk and review effectiveness.
Domain proficiency scale used in the Competence Matrix
1 | Awareness | Recognises concepts, duties and escalation routes; needs guidance for application.
2 | Working | Applies approved instructions in routine scenarios and recognises when to seek specialist advice.
3 | Practitioner | Applies and explains controls in varied cases, exercises judgement and supports others.
4 | Expert / lead | Leads, challenges or independently assures complex application and maintains professional currency.
Appointment, competence and evidence rules
• AIG-GOV-06 and approved Council delegations are the authority source. This workbook operationalises them and cannot create or expand authority.
• Record formal appointments, terms, delegation references, conflict declarations, deputies and review dates in approved Council systems.
• Keep personal data proportionate. Use this register for role-level evidence references; detailed staff learning records should remain in the approved LMS/HR repository.
• Required competency levels describe the role, not the person. Assess each named holder against the role and scope actually assigned.
• Competence may be supported by education, training, professional standing, experience, supervised practice, tests, exercises and observed work.
• Training completion is evidence of participation, not conclusive evidence of competence or authority.
• Define restrictions, supervision, remediation and review dates where competence gaps exist; escalate gaps that affect safe control operation.
• Reassess after material role, system, legal, threat or process change, or after incident, complaint, audit finding or control failure.
• Communications require an approved sender, accessible channel, confidentiality check, retained issue evidence and an effectiveness measure.
• Review effectiveness using completion and assessment results, case quality, rework, incidents, complaints, audits, feedback and AIMS performance.
Source, mapping and controlled-use note
Standard baseline: ISO/IEC 42001:2023, Information technology — Artificial intelligence — Management system.
Official standard page: https://www.iso.org/standard/42001
Primary clauses: 5.3 organisational roles, 7.2 competence, 7.3 awareness, 7.4 communication, 7.5 documented information, 9.1 performance evaluation and 10.1 continual improvement.
Relevant Annex A design links include A.3.2 roles, A.3.3 reporting concerns, A.4.6 human resources, A.8.2-A.8.5 interested-party information and A.9.2 responsible use.
Council sources: AI Governance Playbook (AIG-GOV-02, current controlled version per AIG-GOV-03); AIG-GOV-06 Terms of Reference; AIG-OPS-01 AI Deployment and Rollout Plan; AIG-AIMS-03 Objectives, Risk Treatment and Improvement Plan.
AIG-AIMS-03 linkage: IMP-05 requires approved roles, delegations, RACI and competence/resource plan; IMP-09 requires role-based training and verified competence.
Validate ISO clause and control references against the Council’s licensed standard before formal adoption or certification use.
Control status: draft for Council review. Nothing in this workbook appoints a person, delegates authority, proves competence, records completed training or proves communication effectiveness.

## INTEGRATION INV-04 DEC-04
AIG-AIMS-04 — PROPOSED AIG-INV-04/AIG-DEC-04 INTEGRATION NOTES
NOT APPROVED — additive integration annex only; existing workbook content and formulas are retained unchanged. AIG-INV-04 (AI Register) and AIG-DEC-04 (Gate Log) are themselves proposed designs: until the Council approves their adoption and migration, the Council’s existing records remain authoritative and the AIG-INV-04/AIG-DEC-04 joins below are design references only. No live system, event, evidence, approval or Council decision is asserted.
Review topic | Targeted proposed integration note
Status / authority | The named functions, role profiles, communications and training are proposed role design; no person, committee, appointment, competence, course completion, communication or authority is evidenced by this annex. Confirm positions and delegations against the current Council Constitution/Scheme of Delegation and retain authorised appointment evidence.
Role-to-system join | Use AIR-ID from proposed AIG-INV-04 AI Register to relate the designated Service Owner/System Owner and applicable specialist responsibility to a particular system. The role plan remains the controlled AIMS role/competence source: avoid copying names, contact details, HR data or role definitions into AIG-INV-04/AIG-DEC-04; store only role references needed for a join.
Decision and condition ownership | For each actual gate, AIG-DEC-04 Gate plan may identify the proposed responsible role; Gate events records the actual event/actor and its evidence/decision reference; Conditions holds the action owner/role and due date per condition. Confirm the individual’s appointment, authority and competence in the appropriate controlled source. An event’s actor or an owner label is not proof of delegation.
Competence evidence | Connect role-based competence/assessment evidence to the related AIR-ID only when system-specific competence is material; otherwise maintain AIMS-level role evidence. Use a minimal Evidence ID/source pointer in AIG-INV-04 Evidence index where approved. Training attendance alone does not establish assessed competence; do not place sensitive personnel details in the register or gate workbook.
Communications evidence | Keep each communication plan’s audience, sender/approver, channel, timing, accessibility, consultation and required record in this workbook. When a communication relates to a specific system or gate, reference AIR-ID and, if relevant, Event ID/Condition ID plus Evidence ID; retain issued version and audience evidence in the authorised source. Planned communications are not issued communications.
Escalation / change | Role vacancy, expired competence, changed authority, missed training, inaccessible communication or unavailable specialist capacity should be risk-assessed and escalated via the approved governance route. Record a dated AIG-DEC-04 event only when an actual forum/event occurs; update current register state only through authorised change, with AIG-DEC-03/native decision and supporting evidence.
Open adoption checks | Validate role ownership, deputies, resource/capacity commitments, competence criteria and evidence-retention arrangements with HR/L&D and relevant control functions. Confirm communications approval and record systems; do not claim clause 5.3/7.1–7.4 operation on this designed plan alone.

## STANDARDS SCOPE QA
PROPOSED QA INDEX — NOT APPROVED. A source reference does not establish applicability or compliance. See AIG-AIMS-05 and AIG-AIMS-13; owners must validate the current source, case-specific scope, control evidence and adopted status.
Requirement ID | Instrument / edition | Conditional scope / relevance | Source URL | Owner validation status
REQ-027 | Public Interest Disclosure Act 1998 / Employment Rights Act whistleblowing protections | Screen the legislation requirement against this artefact's actual use and record evidence/version; see the AIG-AIMS-05 Applicable Requirements entry (REQ-027) for the controlled position. | https://www.legislation.gov.uk/ukpga/1998/23/contents | Specialist validation required
REQ-040 | ISO/IEC 42001:2023 Artificial intelligence management system | Proposed management-system design mapping; licensed clause review and adoption needed. | https://www.iso.org/standard/42001 | Specialist validation required

## MAP & SPLIT CONTRACT
AIG-AIMS-04 / PROPOSED THREE-ARTEFACT SOURCE CONTRACT
Status | PROPOSED INTEGRATION DESIGN ONLY. This sheet does not amend the artefact's native assessment, decision authority, data or formulas.
Role of this file | Competence and roles: Train the Service Owner on AIG-INV-03 facts, AIG-INV-04 handoff, and review of UC/CAP links; technical owners own component facts, specialists own their assessments; only delegated forums decide.
AIG-INV-04 source | Separate AIG-INV-04 AI Register: official AIR-ID, current position, in-file Assessment summary/Evidence index. Reconcile against authoritative AIG-INV-04 before using a copied value.
AIG-DEC-04 source | Separate AIG-DEC-04 Gate Log: prospective Gate plan, dated Gate events, event-linked Conditions. A planned gate is not a decision. A decision requires AIG-DEC-03 or approved minutes and proper delegation.
Map source | Proposed standalone Capabilities and System Map (candidate catalogue ID AIG-INV-05): UC/CAP and component relationship pointers. Edge ID is not an approval or permission; AIG-AGT-04/AIG-AGT-05 remain sources of agent scope/authority.
Data exchange | Use controlled AIR-ID across files. Where applicable reference exact Event ID, Condition ID, Evidence ID, AG-ID and Edge ID. Record source file/version/as-at with imported or quoted evidence; no live cross-workbook formula is assumed.
Change trigger | New or expanded system/tool access, or a material model, data, interface, purpose or agent change: log the map change, obtain owner reassessment and escalate to the proper AIG-DEC-04 gate/AIG-DEC-03 decision when required.
Validation before use | The INTEGRATION INV-04 DEC-04 tab in this workbook is current supporting design guidance (not historical) and holds the detailed join notes. Controlled owners must reconcile real records, validate values and formulas in Excel, and approve migration/cutover; existing Council records remain unchanged until then.